## Report (1)
Well Name | Gwendolyn #2612 LB |  |  | Date | 2018-05-23 |  | Report # | 1 | Depth | 883 | Footage | 843 | Planned TD | 1177 | Pad Location | 2-2
Op at RT | Drilling 17 1/2"" Surface hole @ 883' |  |  |  |  | Daily Cost | 176978 |  | Deviation Surveys
Contr/Rig # | Transcend Rig 1 |  |  | Total Days |  | Total Cost | 176978 |  | MD | Angle | Azimuth | TVD | DLS | +N/-S | +E/-W | Closure D | Closure A | Hole Section Codes
Mud WT. | Vis | PV | YP | Gels | API WL | pH | Solids | Chlorides | 90' | 0.9 | 127 | [6 empty] | 1 | Surface
8.3 | 27 | [7 empty] | 210' | 0.4 | 210 | [6 empty] | 2 | Intermediate
HTHP | OWR | ES | WPS | LGS | 6 RPM | 3 RPM | Diesel Rate | Water Rate | 301' | 0.2 | 317 | [6 empty] | 3 | Intermediate 2
[9 empty] | 395' | 0.5 | 197 | [6 empty] | 4 | Production
Diesel Daily | Diesel Total | +Gain/-Loss | Cntrfg Hrs | Torque and Drag Summary |  |  |  |  | 520' | 0.7 | 121
|  |  |  | Depth | Torque | Rot. wt. | PU wt. | SO wt. | 613' | 0.3 | 239 | [6 empty] | IADC OP Codes
Mud Product Used Last 24 hours | [17 empty] | 1 | Rig Up and Tear Down
8 Poly Stks, 12 SAPP Stks, 8 Soap Stks | [17 empty] | 2 | Drill Actual
[18 empty] | 3 | Reaming
[18 empty] | 4 | Coring
Drill Pipe Chemical Used Last 24 hours | [17 empty] | 5 | Condition Mud and Circulate
[18 empty] | 6 | Trips
[9 empty] | Last Survey Proximity to Plan Line |  |  |  | A/B |  | L/R |  |  | 7 | Lubricate Rig
From | To | Hours | Op Code | Activity for Previous 24 Hours | [13 empty] | 8 | Repair Rig
6:00 | 1:00 | 7 | 1.1 | On the Gwendolyn 2611 LA. | [13 empty] | 9 | Cut Off Drilling Line
1:00 | 19:30 | 6.5 | 1.1 | Move and rig up on the Gwendolyn 2612 LA | [13 empty] | 10 | Deviation Survey
19:30 | 6:00 | 10.5 | 1.2 | Spud 17 1/2" surface hole Drlg f/ 40' t/ 883'/ 843'/ 80.2 FPH/ WOB 10-18, Rot 50-85 | [13 empty] | 11 | Wireline Logs
6:00 | [17 empty] | 12 | Run Casing and Cement
0:00 | [17 empty] | 13 | Wait on Cement
0:00 | [17 empty] | 14 | Nipple Up BOP
0:00 | [17 empty] | 15 | Test BOP
0:00 | [17 empty] | 16 | Drill Stem Test
0:00 | [17 empty] | 17 | Plug Back
0:00 | [17 empty] | 18 | Squeeze Cement
0:00 | [17 empty] | 19 | Fishing
0:00 | [17 empty] | 20 | Directional Work
0:00 | [17 empty] | 21 | Non Productive Time
0:00 | [17 empty] | 22
0:00 | [17 empty] | 23
0:00
0:00
0:00
0:00
0:00
0:00 |  |  |  | Notified TRCC of spud @ 7:00 PM on 5/22/2018, Audry Oper #2
0:00
0:00
0:00 |  |  |  | Panther Trucking Del: 32 joints of 13 3/8" casing from Sooner pipe
0:00 |  |  |  | Art's casing inspection. All Casing Good
0:00 |  |  |  | Drilling hours: 10.50
TOTAL HOURS |  | 24
Bit # | Size | Mfg | Type | Part | SN | Jets | In | Out | Ftg | Hrs | ROP | Grade | Gauge | Rsn Pulled | Comments
1 | 17.5 | PDC Logic | KS1963AR |  | 17111528 | 8X16 | 40 | 883 | 843 | 10.5 | 80.2857 |  |  |  | Surface
BHA # | Description | [7 empty] | BHA Lngth | Motor Mfg | Size | Bend | Stab OD | Fixed/Adj | Lobes/Stages | RPG | SN
1 | Bit, Bit Sub, Shock Sub, True Fire, 8" DC, IBS, 8" DC, X/O, 5-6" DC's | [7 empty] | 237.43
|  | size | Wt. | Grade | Conn. | Jts | Length | Jts / Loc | String Volume |  |  |  | Size | Wt/Grade | Bottom | Top | Date Set
Drill Pipe (bottom) |  | 4.5 | 16.6 | G 105 | 4.5 XH | 21 | 645.57 |  |  | bbls. | Conductor |  | 20 | 52.78 / B | 50 | 0'
Drill Pipe (middle) | [10 empty] | Surface Casing |  | 13.375 | 54.50 / J-55 |  | 0'
Drill Pipe (top) | [10 empty] | Intermediate Csg
Assumed Pump Eff. |  | Pump No. 1 |  | 90% | Pump No. 2 |  | 95% | Slow Pump Rate/Press |  |  | Intermediate 2 Csg
| Type | Liner OD | Length | GPS (100%) | SPM | GPM | Press | Depth | SPM | Pressure | Production Casing
Pump No. 1 | PZ-8 | 6.5 | 8 | 3.83 | 120 | 413.64 | 450 |  |  |  | Personnel Summary |  |  | Contact Information
Pump No. 2 | [5 empty] | 0 |  |  |  |  | Rig Crew Days |  | 4 | Foreman Days |  | Richard Hardwick
Surface Rig Spud Date |  | 2018-05-22 | Time | 19:30 | Loads/bbls FW Hauled |  |  | Item | Serial Number |  | Rig Crew Nights |  | 4 | Phone |  | (432) 553-6153
Surface Rig Release Date |  |  | Time |  | Loads/bbls BW Hauled |  |  | Stab 1 |  |  | Toolpusher |  | 1 | Foreman Nights
Rig Spud Date |  |  | Time |  | Loads/bbls Res Hauled |  |  | Stab 2 |  |  | Company Formen |  | 1 | Phone
Rig Pause Date |  |  | Time |  | Loads Gel Hauled |  |  | Stab 3 |  |  | Directional Drillers |  |  | Toolpusher |  | Greg De La Rosa
Rig Resume Date |  |  | Time |  | Loads Barite Hauled |  |  | Surv Tool |  |  | MWD |  |  | Phone |  | (432) 556-2220
Rig Release Date |  |  | Time |  | Loads OBM Cuttings |  |  | Bit Sub |  |  | Mud Engineer |  |  | Directional Days
Incident/Safety Information | [7 empty] | Shock Sub |  |  | Solids Control |  |  | Phone
No accidents reported last 24 hours | [7 empty] | Agitator |  |  | Other |  |  | Directional Nights
[8 empty] | NMDC |  |  | Total Personnel |  | 10 | Phone
Well Name | Gwendolyn #2612 LB |  |  | Date | 2018-05-23 |  | Report # | 1 | Depth | 883 | Footage | 843
Op at RT | Drilling 17 1/2"" Surface hole @ 883' |  |  |  |  | Daily Cost | 176978 |  | Deviation Surveys
Contr/Rig # | Transcend Rig 1 |  |  | Total Days |  | Total Cost | 176978 |  | MD | Angle | Azimuth | TVD
Bit No. | Size | In | Out | Ftg | Hrs | ROP | Grade | Rsn Pulled | 90' | 0.9 | 127 | 0
1 | 17.5 | 40 | 883 | 843 | 10.5 | 80.2857 | 0 | 0 | 210' | 0.4 | 210 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 301' | 0.2 | 317 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 395' | 0.5 | 197 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 520' | 0.7 | 121 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 613' | 0.3 | 239 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Size | Wt/Grade | Bottom | Top | Date Set | Mud Wt. | 8.3 | 0 | 0 | 0 | 0
Conductor |  | 20 | 52.78 / B | 50 | 0' | 0 | Vis | 27 | 0 | 0 | 0 | 0
Surface Casing |  | 13.375 | 54.50 / J-55 | 0 | 0' | 0 | pH | 0 | 0 | 0 | 0 | 0
Intermediate Csg |  | 0 | 0 | 0 | 0 | 0 | API WL | 0
Intermediate 2 Csg |  | 0 | 0 | 0 | 0 | 0 | Chlorides | 0
Production Casing |  | 0 | 0 | 0 | 0 | 0 | OWR | 0
Surface Rig Spud Date |  | 2018-05-22 | Time | 19:30 | Rig Pause Date |  | 0 | Time | 0:00
Surface Rig Release Date |  | 0 | Time | 0:00 | Rig Resume Date |  | 0 | Time | 0:00
Rig Spud Date |  | 0 | Time | 0:00 | Rig Release Date |  | 0 | Time | 0:00

## Report (2)
Well Name | Gwendolyn #2612 LB |  |  | Date | 2018-05-24 |  | Report # | 2 | Depth | 1177 | Footage | 294 | Planned TD | 1177 | Pad Location | 2-2
Op at RT | Cementing 13 3/8" Casing |  |  |  |  | Daily Cost | 2029 |  | Deviation Surveys
Contr/Rig # | Transcend Rig 1 |  |  | Total Days |  | Total Cost | 179006 |  | MD | Angle | Azimuth | TVD | DLS | +N/-S | +E/-W | Closure D | Closure A | Hole Section Codes
Mud WT. | Vis | PV | YP | Gels | API WL | pH | Solids | Chlorides | 707 | 0.5 | 47 | [6 empty] | 1 | Surface
8.3 | 27 | [7 empty] | 802 | 0.2 | 355 | [6 empty] | 2 | Intermediate
HTHP | OWR | ES | WPS | LGS | 6 RPM | 3 RPM | Diesel Rate | Water Rate | 896 | 0.3 | 43 | [6 empty] | 3 | Intermediate 2
[9 empty] | 992 | 0.3 | 43 | [6 empty] | 4 | Production
Diesel Daily | Diesel Total | +Gain/-Loss | Cntrfg Hrs | Torque and Drag Summary |  |  |  |  | 1087 | 0.4 | 242
|  |  |  | Depth | Torque | Rot. wt. | PU wt. | SO wt. | 1177 | 0.5 | 231 | [6 empty] | IADC OP Codes
Mud Product Used Last 24 hours | [17 empty] | 1 | Rig Up and Tear Down
8 Poly Stks, 12 SAPP Stks, 8 Soap Stks | [17 empty] | 2 | Drill Actual
[18 empty] | 3 | Reaming
[18 empty] | 4 | Coring
Drill Pipe Chemical Used Last 24 hours | [17 empty] | 5 | Condition Mud and Circulate
[18 empty] | 6 | Trips
[9 empty] | Last Survey Proximity to Plan Line |  |  |  | A/B |  | L/R |  |  | 7 | Lubricate Rig
From | To | Hours | Op Code | Activity for Previous 24 Hours | [13 empty] | 8 | Repair Rig
6:00 | 6:30 | 0.5 | 1.21 | PJSM w/ Rig Crew | [13 empty] | 9 | Cut Off Drilling Line
6:30 | 15:00 | 8.5 | 1.2 | (Surface) Rotate Drill F/883' - T/1156' (273' @ 32FPH) WOB 10-18, Rot 50-85 | [13 empty] | 10 | Deviation Survey
15:00 | 16:30 | 1.5 | 1.8 | Change out Washpipe and Packing | [13 empty] | 11 | Wireline Logs
16:30 | 18:00 | 1.5 | 1.2 | (Surface) Rotate Drill F/1156' - T/1177' (21' @ 14FPH) WOB 10-18, Rot 50-85 | [13 empty] | 12 | Run Casing and Cement
18:00 | 18:30 | 0.5 | 1.21 | PJSM w/ Rig Crew | [13 empty] | 13 | Wait on Cement
18:30 | 19:00 | 0.5 | 1.5 | Circulate Clean Hole | [13 empty] | 14 | Nipple Up BOP
19:00 | 21:30 | 2.5 | 1.6 | TOH, Break Down BHA | [13 empty] | 15 | Test BOP
21:30 | 22:00 | 0.5 | 1.12 | Prep and RU to Run Casing | [13 empty] | 16 | Drill Stem Test
22:00 | 1:00 | 3 | 1.12 | Make up Shoe track and wait on welder to Weld Float Collar and 2nd Joint | [13 empty] | 17 | Plug Back
1:00 | 4:00 | 3 | 1.12 | Run Casing F/86' - T/1177' | [13 empty] | 18 | Squeeze Cement
4:00 | 5:00 | 1 | 1.5 | Circulate and PJSM with Cementers | [13 empty] | 19 | Fishing
5:00 | 6:00 | 1 | 1.12 | RU and Cement 13 3/8" Casing as per prog | [13 empty] | 20 | Directional Work
6:00 | [17 empty] | 21 | Non Productive Time
0:00 | [17 empty] | 22
0:00 | [17 empty] | 23
0:00
0:00
0:00
0:00
0:00
0:00 |  |  |  | Notified TRCC of spud @ 7:00 PM on 5/22/2018, Audry Oper #2
0:00
0:00
0:00 |  |  |  | Panther Trucking Del: 32 joints of 13 3/8" casing from Sooner pipe
0:00 |  |  |  | Art's casing inspection. All Casing Good
0:00 |  |  |  | Drilling hours: 10.50
TOTAL HOURS |  | 24
Bit # | Size | Mfg | Type | Part | SN | Jets | In | Out | Ftg | Hrs | ROP | Grade | Gauge | Rsn Pulled | Comments
1 | 17.5 | PDC Logic | KS1963AR |  | 17111528 | 8X16 | 40 | 1177 | 1137 | 20.5 | 55.4634 | 1,1 | In | TD | Surface
BHA # | Description | [7 empty] | BHA Lngth | Motor Mfg | Size | Bend | Stab OD | Fixed/Adj | Lobes/Stages | RPG | SN
1 | Bit, Bit Sub, Shock Sub, True Fire, 8" DC, IBS, 8" DC, X/O, 5-6" DC's | [7 empty] | 237.43
|  | size | Wt. | Grade | Conn. | Jts | Length | Jts / Loc | String Volume |  |  |  | Size | Wt/Grade | Bottom | Top | Date Set
Drill Pipe (bottom) |  | 4.5 | 16.6 | G 105 | 4.5 XH | 21 | 645.57 |  |  | bbls. | Conductor |  | 20 | 52.78 / B | 50 | 0'
Drill Pipe (middle) | [10 empty] | Surface Casing |  | 13.375 | 54.50 / J-55 |  | 0'
Drill Pipe (top) | [10 empty] | Intermediate Csg
Assumed Pump Eff. |  | Pump No. 1 |  | 90% | Pump No. 2 |  | 95% | Slow Pump Rate/Press |  |  | Intermediate 2 Csg
| Type | Liner OD | Length | GPS (100%) | SPM | GPM | Press | Depth | SPM | Pressure | Production Casing
Pump No. 1 | PZ-8 | 6.5 | 8 | 3.83 | 120 | 413.64 | 450 |  |  |  | Personnel Summary |  |  | Contact Information
Pump No. 2 | [5 empty] | 0 |  |  |  |  | Rig Crew Days |  | 4 | Foreman Days |  | Cody Keel
Surface Rig Spud Date |  | 2018-05-22 | Time | 19:30 | Loads/bbls FW Hauled |  |  | Item | Serial Number |  | Rig Crew Nights |  | 4 | Phone |  | (325)232-9610
Surface Rig Release Date |  |  | Time |  | Loads/bbls BW Hauled |  |  | Stab 1 |  |  | Toolpusher |  | 1 | Foreman Nights
Rig Spud Date |  |  | Time |  | Loads/bbls Res Hauled |  |  | Stab 2 |  |  | Company Formen |  | 1 | Phone
Rig Pause Date |  |  | Time |  | Loads Gel Hauled |  |  | Stab 3 |  |  | Directional Drillers |  |  | Toolpusher |  | Carlos Lopez
Rig Resume Date |  |  | Time |  | Loads Barite Hauled |  |  | Surv Tool |  |  | MWD |  |  | Phone |  | (325) 812-3464
Rig Release Date |  |  | Time |  | Loads OBM Cuttings |  |  | Bit Sub |  |  | Mud Engineer |  |  | Directional Days
Incident/Safety Information | [7 empty] | Shock Sub |  |  | Solids Control |  |  | Phone
No accidents reported last 24 hours | [7 empty] | Agitator |  |  | Other |  |  | Directional Nights
[8 empty] | NMDC |  |  | Total Personnel |  | 10 | Phone
Well Name | Gwendolyn #2612 LB |  |  | Date | 2018-05-24 |  | Report # | 2 | Depth | 1177 | Footage | 294
Op at RT | Cementing 13 3/8" Casing |  |  |  |  | Daily Cost | 2029 |  | Deviation Surveys
Contr/Rig # | Transcend Rig 1 |  |  | Total Days |  | Total Cost | 179006 |  | MD | Angle | Azimuth | TVD
Bit No. | Size | In | Out | Ftg | Hrs | ROP | Grade | Rsn Pulled | 707 | 0.5 | 47 | 0
1 | 17.5 | 40 | 1177 | 1137 | 20.5 | 55.4634 | 1,1 | TD | 802 | 0.2 | 355 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 896 | 0.3 | 43 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 992 | 0.3 | 43 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 1087 | 0.4 | 242 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 1177 | 0.5 | 231 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Size | Wt/Grade | Bottom | Top | Date Set | Mud Wt. | 8.3 | 0 | 0 | 0 | 0
Conductor |  | 20 | 52.78 / B | 50 | 0' | 0 | Vis | 27 | 0 | 0 | 0 | 0
Surface Casing |  | 13.375 | 54.50 / J-55 | 0 | 0' | 0 | pH | 0 | 0 | 0 | 0 | 0
Intermediate Csg |  | 0 | 0 | 0 | 0 | 0 | API WL | 0
Intermediate 2 Csg |  | 0 | 0 | 0 | 0 | 0 | Chlorides | 0
Production Casing |  | 0 | 0 | 0 | 0 | 0 | OWR | 0
Surface Rig Spud Date |  | 2018-05-22 | Time | 19:30 | Rig Pause Date |  | 0 | Time | 0:00
Surface Rig Release Date |  | 0 | Time | 0:00 | Rig Resume Date |  | 0 | Time | 0:00
Rig Spud Date |  | 0 | Time | 0:00 | Rig Release Date |  | 0 | Time | 0:00

## Report (3)
Well Name | Gwendolyn #2612 LB |  |  | Date | 2018-05-25 |  | Report # | 3 | Depth | 1177 | Footage | 0 | Planned TD | 1177 | Pad Location | 2-2
Op at RT | Rig is Released and Waiting to Move |  |  |  |  | Daily Cost | 65816 |  | Deviation Surveys
Contr/Rig # | Transcend Rig 1 |  |  | Total Days |  | Total Cost | 244822 |  | MD | Angle | Azimuth | TVD | DLS | +N/-S | +E/-W | Closure D | Closure A | Hole Section Codes
Mud WT. | Vis | PV | YP | Gels | API WL | pH | Solids | Chlorides | [9 empty] | 1 | Surface
8.3 | 27 | [16 empty] | 2 | Intermediate
HTHP | OWR | ES | WPS | LGS | 6 RPM | 3 RPM | Diesel Rate | Water Rate | [9 empty] | 3 | Intermediate 2
[18 empty] | 4 | Production
Diesel Daily | Diesel Total | +Gain/-Loss | Cntrfg Hrs | Torque and Drag Summary
|  |  |  | Depth | Torque | Rot. wt. | PU wt. | SO wt. | [9 empty] | IADC OP Codes
Mud Product Used Last 24 hours | [17 empty] | 1 | Rig Up and Tear Down
[18 empty] | 2 | Drill Actual
[18 empty] | 3 | Reaming
[18 empty] | 4 | Coring
Drill Pipe Chemical Used Last 24 hours | [17 empty] | 5 | Condition Mud and Circulate
[18 empty] | 6 | Trips
[9 empty] | Last Survey Proximity to Plan Line |  |  |  | A/B |  | L/R |  |  | 7 | Lubricate Rig
From | To | Hours | Op Code | Activity for Previous 24 Hours | [13 empty] | 8 | Repair Rig
6:00 | 6:30 | 0.5 | 1.12 | PJSM w/ Rig Crews and Continue Cementing as Per Prog | [13 empty] | 9 | Cut Off Drilling Line
6:30 | 7:30 | 1 | 1.13 | WOC and RD Cementers | [13 empty] | 10 | Deviation Survey
7:30 | 12:30 | 5 | 1.13 | WOC | [13 empty] | 11 | Wireline Logs
12:30 | 13:30 | 1 | 1.21 | Cut Casing | [13 empty] | 12 | Run Casing and Cement
13:30 | 18:00 | 4.5 | 1.1 | Rig Down Back Yard, Layover Derrick and Remove Rig From Hole | [13 empty] | 13 | Wait on Cement
18:00 | 18:30 | 0.5 | 1.21 | PJSM w/ Rig Crews | [13 empty] | 14 | Nipple Up BOP
18:30 | 6:00 | 11.5 | 1.1 | Pressure wash Equipment and Organize location for Rig Move | [13 empty] | 15 | Test BOP
6:00 | [17 empty] | 16 | Drill Stem Test
0:00 | [17 empty] | 17 | Plug Back
0:00 | [17 empty] | 18 | Squeeze Cement
0:00 |  |  |  | Plug Down 5-24-18 @ 06:34am | [13 empty] | 19 | Fishing
0:00 | [17 empty] | 20 | Directional Work
0:00 | [17 empty] | 21 | Non Productive Time
0:00 | [17 empty] | 22
0:00 | [17 empty] | 23
0:00
0:00
0:00
0:00
0:00
0:00 |  |  |  | Notified TRCC of spud @ 7:00 PM on 5/22/2018, Audry Oper #2
0:00
0:00
0:00 |  |  |  | Panther Trucking Del: 32 joints of 13 3/8" casing from Sooner pipe
0:00 |  |  |  | Art's casing inspection. All Casing Good
0:00 |  |  |  | Drilling hours: 10.50
TOTAL HOURS |  | 24
Bit # | Size | Mfg | Type | Part | SN | Jets | In | Out | Ftg | Hrs | ROP | Grade | Gauge | Rsn Pulled | Comments
1 | 17.5 | PDC Logic | KS1963AR |  | 17111528 | 8X16 | 40 | 1177 | 1137 | 20.5 | 55.4634 | 1,1 | In | TD | Surface
BHA # | Description | [7 empty] | BHA Lngth | Motor Mfg | Size | Bend | Stab OD | Fixed/Adj | Lobes/Stages | RPG | SN
1 | Bit, Bit Sub, Shock Sub, True Fire, 8" DC, IBS, 8" DC, X/O, 5-6" DC's | [7 empty] | 237.43
|  | size | Wt. | Grade | Conn. | Jts | Length | Jts / Loc | String Volume |  |  |  | Size | Wt/Grade | Bottom | Top | Date Set
Drill Pipe (bottom) |  | 4.5 | 16.6 | G 105 | 4.5 XH | 21 | 645.57 |  |  | bbls. | Conductor |  | 20 | 52.78 / B | 50 | 0'
Drill Pipe (middle) | [10 empty] | Surface Casing |  | 13.375 | 54.50 / J-55 |  | 0'
Drill Pipe (top) | [10 empty] | Intermediate Csg
Assumed Pump Eff. |  | Pump No. 1 |  | 90% | Pump No. 2 |  | 95% | Slow Pump Rate/Press |  |  | Intermediate 2 Csg
| Type | Liner OD | Length | GPS (100%) | SPM | GPM | Press | Depth | SPM | Pressure | Production Casing
Pump No. 1 | PZ-8 | 6.5 | 8 | 3.83 | 120 | 413.64 | 450 |  |  |  | Personnel Summary |  |  | Contact Information
Pump No. 2 | [5 empty] | 0 |  |  |  |  | Rig Crew Days |  | 4 | Foreman Days |  | Cody Keel
Surface Rig Spud Date |  | 2018-05-22 | Time | 19:30 | Loads/bbls FW Hauled |  |  | Item | Serial Number |  | Rig Crew Nights |  | 4 | Phone |  | (325)232-9610
Surface Rig Release Date |  | 2018-05-24 | Time | 13:30 | Loads/bbls BW Hauled |  |  | Stab 1 |  |  | Toolpusher |  | 1 | Foreman Nights
Rig Spud Date |  |  | Time |  | Loads/bbls Res Hauled |  |  | Stab 2 |  |  | Company Formen |  | 1 | Phone
Rig Pause Date |  |  | Time |  | Loads Gel Hauled |  |  | Stab 3 |  |  | Directional Drillers |  |  | Toolpusher |  | Carlos Lopez
Rig Resume Date |  |  | Time |  | Loads Barite Hauled |  |  | Surv Tool |  |  | MWD |  |  | Phone |  | (325) 812-3464
Rig Release Date |  |  | Time |  | Loads OBM Cuttings |  |  | Bit Sub |  |  | Mud Engineer |  |  | Directional Days
Incident/Safety Information | [7 empty] | Shock Sub |  |  | Solids Control |  |  | Phone
No accidents reported last 24 hours | [7 empty] | Agitator |  |  | Other |  |  | Directional Nights
[8 empty] | NMDC |  |  | Total Personnel |  | 10 | Phone
Well Name | Gwendolyn #2612 LB |  |  | Date | 2018-05-25 |  | Report # | 3 | Depth | 1177 | Footage | 0
Op at RT | Rig is Released and Waiting to Move |  |  |  |  | Daily Cost | 65816 |  | Deviation Surveys
Contr/Rig # | Transcend Rig 1 |  |  | Total Days |  | Total Cost | 244822 |  | MD | Angle | Azimuth | TVD
Bit No. | Size | In | Out | Ftg | Hrs | ROP | Grade | Rsn Pulled | 0 | 0 | 0 | 0
1 | 17.5 | 40 | 1177 | 1137 | 20.5 | 55.4634 | 1,1 | TD | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Size | Wt/Grade | Bottom | Top | Date Set | Mud Wt. | 8.3 | 0 | 0 | 0 | 0
Conductor |  | 20 | 52.78 / B | 50 | 0' | 0 | Vis | 27 | 0 | 0 | 0 | 0
Surface Casing |  | 13.375 | 54.50 / J-55 | 0 | 0' | 0 | pH | 0 | 0 | 0 | 0 | 0
Intermediate Csg |  | 0 | 0 | 0 | 0 | 0 | API WL | 0
Intermediate 2 Csg |  | 0 | 0 | 0 | 0 | 0 | Chlorides | 0
Production Casing |  | 0 | 0 | 0 | 0 | 0 | OWR | 0
Surface Rig Spud Date |  | 2018-05-22 | Time | 19:30 | Rig Pause Date |  | 0 | Time | 0:00
Surface Rig Release Date |  | 2018-05-24 | Time | 13:30 | Rig Resume Date |  | 0 | Time | 0:00
Rig Spud Date |  | 0 | Time | 0:00 | Rig Release Date |  | 0 | Time | 0:00

## Report (4)
Well Name | Gwendolyn #2612 LB |  |  | Date | 2018-06-24 |  | Report # | 4 | Depth | 1860 | Footage | 683 | Planned TD | 8518 | Pad Location | 2-2
Op at RT | (Intermediate) Drilling 12 1/4" hole @ 1860' |  |  |  |  | Daily Cost | 76397 |  | Deviation Surveys
Contr/Rig # | Precision Rig 593 |  |  | Total Days | 2.6146 | Total Cost | 321219 |  | MD | Angle | Azimuth | TVD | DLS | +N/-S | +E/-W | Closure D | Closure A | Hole Section Codes
Mud WT. | Vis | PV | YP | Gels | API WL | pH | Solids | Chlorides | 1316' | 0.74 | 202.72 | 1315.96 | 0.27 | -4.67 | 0.8 | 4.73 | 170.33 | 1 | Surface
8.9 | 30 |  |  |  |  | 11 |  |  | 1406' | 0.65 | 218.46 | 1405.95 | 0.23 | -5.6 | 0.25 | 5.61 | 177.41 | 2 | Intermediate
HTHP | OWR | ES | WPS | LGS | 6 RPM | 3 RPM | Diesel Rate | Water Rate | 1495' | 0.76 | 201.29 | 1494.95 | 0.27 | -6.55 | -0.28 | 6.55 | 182.41 | 3 | Intermediate 2
[9 empty] | 1584' | 0.74 | 206.7 | 1583.94 | 0.08 | -7.61 | -0.75 | 7.65 | 185.61 | 4 | Production
Diesel Daily | Diesel Total | +Gain/-Loss | Cntrfg Hrs | Torque and Drag Summary |  |  |  |  | 1674' | 0.84 | 199.69 | 1673.93 | 0.15 | -8.75 | -1.23 | 8.84 | 188.01
|  |  |  | Depth | Torque | Rot. wt. | PU wt. | SO wt. | 1764' | 0.97 | 196.56 | 1763.92 | 0.15 | -10.1 | -1.67 | 10.24 | 189.39 | IADC OP Codes
Mud Product Used Last 24 hours |  |  |  | 1554' | 8 to 11 | 132 | 142 | 132 | [9 empty] | 1 | Rig Up and Tear Down
Lime 15, Soda ash 10, Soap sticks 9, MF-55 2, |  |  |  | 1700 | 8 to 13 | 136 | 140 | 136 | [9 empty] | 2 | Drill Actual
[18 empty] | 3 | Reaming
[18 empty] | 4 | Coring
Drill Pipe Chemical Used Last 24 hours | [17 empty] | 5 | Condition Mud and Circulate
[18 empty] | 6 | Trips
[9 empty] | Last Survey Proximity to Plan Line |  |  |  | A/B | 9 B | L/R | 5 L |  | 7 | Lubricate Rig
From | To | Hours | Op Code | Activity for Previous 24 Hours | [13 empty] | 8 | Repair Rig
6:00 | 10:45 | 4.75 | 2.1 | Nipple down and walk rig from the Gwendolyn 2611 LA. Center over well @ 10:45 AM | [13 empty] | 9 | Cut Off Drilling Line
10:45 | 15:30 | 4.75 | 2.14 | Nipple up B.O.P | [13 empty] | 10 | Deviation Survey
15:30 | 19:15 | 3.75 | 2.15 | Test all manifold valves, Set test plug, Test blind rams, lower & upper rams, mud lines, annular, floor valves, manual ibop 1500 hi/ 300 lo for 5 mins/ test | [13 empty] | 11 | Wireline Logs
19:15 | 20:00 | 0.75 | 2.15 | Test casing 1500 psi for 30 min | [13 empty] | 12 | Run Casing and Cement
20:00 | 20:15 | 0.25 | 2.21 | Install wear bushing | [13 empty] | 13 | Wait on Cement
20:15 | 21:45 | 1.5 | 2.20. | Pick & make directional tools, scribe, pulse test mwd & make up bit | [13 empty] | 14 | Nipple Up BOP
21:45 | 22:30 | 0.75 | 2.6 | T.I.H w/ bha | [13 empty] | 15 | Test BOP
22:30 | 23:00 | 0.5 | 2.6 | T.I.H w/ drill pipe f/ 660' t/ 1072' | [13 empty] | 16 | Drill Stem Test
23:00 | 24:00 | 1 | 2.9 | Slip & cut drill line 88' | [13 empty] | 17 | Plug Back
24:00 | 12:45 | 0.75 | 2.21 | Drill out shoe track | [13 empty] | 18 | Squeeze Cement
12:45 | 2:00 | 1.25 | 2.2 | Intermediate 12 1/4" hole Rot f/ 1177' t/ 1375'/ 198'/ 158.4 FPH/ WOB 25/ GPM 500-654/ RPM 25-40/ MRPM 83-108/ TQ 7-9 | [13 empty] | 19 | Fishing
2:00 | 2:30 | 0.5 | 2.20. | MWD for correction | [13 empty] | 20 | Directional Work
2:30 | 4:00 | 1.5 | 2.2 | Intermediate 12 1/4" hole Rot f/ 1375' t/ 1643'/ 268'/ 178.6 FPH/ WOB 25/ GPM 654-750/ RPM 40-55/ MRPM 108-125/ TQ 7-11 | [13 empty] | 21 | Non Productive Time
4:00 | 4:30 | 0.5 | 2.7 | Rig service | [13 empty] | 22
4:30 | 6:00 | 1.5 | 2.2 | Intermediate 12 1/4" hole Rot f/ 1643' t/ 1860'/ 217'/ 144.6 FPH/ WOB 25/ GPM 750/ RPM 55/ MRPM 125/ TQ 7-11 | [13 empty] | 23
6:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
TOTAL HOURS |  | 24 |  | Drilling Hrs: 4.25 Fresh water gel tanks 2500 Shaker Screens RRC #
Bit # | Size | Mfg | Type | Part | SN | Jets | In | Out | Ftg | Hrs | ROP | Grade | Gauge | Rsn Pulled | Comments
1 | 17.5 | PDC Logic | KS1963AR |  | 17111528 | 8X16 | 40 | 1177 | 1137 | 20.5 | 55.4634 | 1,1 | In | TD | Surface
2 | 12.25 | Ulterra | CF 616 | U03001 | 39972 | 6 X 16 | 1177 | 1860 | 683 | 4.25 | 160.7059 |  |  |  | Intermediate
BHA # | Description | [7 empty] | BHA Lngth | Motor Mfg | Size | Bend | Stab OD | Fixed/Adj | Lobes/Stages | RPG | SN
1 | Bit, Bit Sub, Shock Sub, True Fire, 8" DC, IBS, 8" DC, X/O, 5-6" DC's | [7 empty] | 237.43
2 | 12 1/4" bit, Motor #1, 11 3/4" Stab, UBHO, 2-NMDC, 11 3/4" Stab, 6-8" DC's, X/O, 12-6 1/2" DC's, X/O | [7 empty] | 660.53 | Renagade | 9 5/8 | 1.5 | 11.5 | Fixed | 7/8: 4.0 | .166 | RDM 911
|  | size | Wt. | Grade | Conn. | Jts | Length | Jts / Loc | String Volume |  |  |  | Size | Wt/Grade | Bottom | Top | Date Set
Drill Pipe (bottom) |  | 5 | 19.5 | S-135 | 4.5 IF |  |  |  | 25.8 | bbls. | Conductor |  | 20 | 52.78 / B | 50 | 0'
Drill Pipe (middle) |  | 5 | 49.8 | HWDP | 4.5 IF | [5 empty] | Surface Casing |  | 13.375 | 54.50 / J-55 | 1177 | 0'
Drill Pipe (top) |  | 5 | 19.5 | S-135 | 4.5 IF | 28 | 1252.13 | 443 |  |  | Intermediate Csg
Assumed Pump Eff. |  | Pump No. 1 |  | 95% | Pump No. 2 |  | 95% | Slow Pump Rate/Press |  |  | Intermediate 2 Csg
| Type | Liner OD | Length | GPS (100%) | SPM | GPM | Press | Depth | SPM | Pressure | Production Casing
Pump No. 1 | FB-1600 | 6 | 12 | 4.4 | 90 | 376.2 | 2300 | 1643 | 30 | 120 | Personnel Summary |  |  | Contact Information
Pump No. 2 | FB-1600 | 6 | 12 | 4.4 | 90 | 376.2 | 2300 | 1643 | 30 | 120 | Rig Crew Days |  | 5 | Foreman Days |  | Richard Hardwick
Surface Rig Spud Date |  | 2018-05-22 | Time | 19:30 | Loads/bbls FW Hauled |  |  | Item | Serial Number |  | Rig Crew Nights |  | 6 | Phone |  | (432)553-6153
Surface Rig Release Date |  | 2018-05-24 | Time | 13:30 | Loads/bbls BW Hauled |  |  | Stab 1 | B&A 8626 |  | Toolpusher |  | 1 | Foreman Nights |  | Randall Blue
Rig Spud Date |  | 2018-06-23 | Time | 9:15 | Loads/bbls Res Hauled |  |  | Stab 2 | B&A 87596 |  | Company Formen |  | 2 | Phone |  | (325)315-3200
Rig Pause Date |  |  | Time |  | Loads Gel Hauled |  |  | Stab 3 |  |  | Directional Drillers |  | 2 | Toolpusher |  | Nick Pool
Rig Resume Date |  |  | Time |  | Loads Barite Hauled |  |  | Surv Tool |  |  | MWD |  | 2 | Phone |  | (254) 624-3082
Rig Release Date |  |  | Time |  | Loads OBM Cuttings |  |  | Bit Sub |  |  | Mud Engineer |  |  | Directional Days |  | Wesley Teeter
Incident/Safety Information | [7 empty] | Shock Sub |  |  | Solids Control |  |  | Phone |  | (817) 408-6235
No accidents reported last 24 hours | [7 empty] | Agitator |  |  | Other |  |  | Directional Nights |  | Shane Longmire
[8 empty] | NMDC | DR86229 / DR340115 |  | Total Personnel |  | 18 | Phone |  | (361) 354-4160
Well Name | Gwendolyn #2612 LB |  |  | Date | 2018-06-24 |  | Report # | 4 | Depth | 1860 | Footage | 683
Op at RT | (Intermediate) Drilling 12 1/4" hole @ 1860' |  |  |  |  | Daily Cost | 76397 |  | Deviation Surveys
Contr/Rig # | Precision Rig 593 |  |  | Total Days | 2.6146 | Total Cost | 321219 |  | MD | Angle | Azimuth | TVD
Bit No. | Size | In | Out | Ftg | Hrs | ROP | Grade | Rsn Pulled | 1316' | 0.74 | 202.72 | 1315.96
1 | 17.5 | 40 | 1177 | 1137 | 20.5 | 55.4634 | 1,1 | TD | 1406' | 0.65 | 218.46 | 1405.95
2 | 12.25 | 1177 | 1860 | 683 | 4.25 | 160.7059 | 0 | 0 | 1495' | 0.76 | 201.29 | 1494.95
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 1584' | 0.74 | 206.7 | 1583.94
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 1674' | 0.84 | 199.69 | 1673.93
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 1764' | 0.97 | 196.56 | 1763.92
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Size | Wt/Grade | Bottom | Top | Date Set | Mud Wt. | 8.9 | 0 | 0 | 0 | 0
Conductor |  | 20 | 52.78 / B | 50 | 0' | 0 | Vis | 30 | 0 | 0 | 0 | 0
Surface Casing |  | 13.375 | 54.50 / J-55 | 1177 | 0' | 0 | pH | 11 | 0 | 0 | 0 | 0
Intermediate Csg |  | 0 | 0 | 0 | 0 | 0 | API WL | 0
Intermediate 2 Csg |  | 0 | 0 | 0 | 0 | 0 | Chlorides | 0
Production Casing |  | 0 | 0 | 0 | 0 | 0 | OWR | 0
Surface Rig Spud Date |  | 2018-05-22 | Time | 19:30 | Rig Pause Date |  | 0 | Time | 0:00
Surface Rig Release Date |  | 2018-05-24 | Time | 13:30 | Rig Resume Date |  | 0 | Time | 0:00
Rig Spud Date |  | 2018-06-23 | Time | 9:15 | Rig Release Date |  | 0 | Time | 0:00

## Report (5)
Well Name | Gwendolyn #2612 LB |  |  | Date | 2018-06-25 |  | Report # | 5 | Depth | 4385 | Footage | 2525 | Planned TD | 8518 | Pad Location | 2-2
Op at RT | (Intermediate) Drilling 12 1/4" hole @ 4385' |  |  |  |  | Daily Cost | 46944 |  | Deviation Surveys
Contr/Rig # | Precision Rig 593 |  |  | Total Days | 3.6146 | Total Cost | 368163 |  | MD | Angle | Azimuth | TVD | DLS | +N/-S | +E/-W | Closure D | Closure A | Hole Section Codes
Mud WT. | Vis | PV | YP | Gels | API WL | pH | Solids | Chlorides | 1942' | 0.86 | 338.02 | 1941.91 | 0.99 | -10.32 | -2.86 | 10.71 | 195.47 | 1 | Surface
9.5 | 32 |  |  |  |  | 11 |  |  | 2211' | 4.53 | 342.69 | 2210.58 | 1.53 | 1.53 | -6.26 | 6.45 | 283.76 | 2 | Intermediate
HTHP | OWR | ES | WPS | LGS | 6 RPM | 3 RPM | Diesel Rate | Water Rate | 2480' | 6.39 | 339.06 | 2478.21 | 0.32 | 27 | -15.2 | 30.98 | 330.62 | 3 | Intermediate 2
[9 empty] | 2748' | 6.82 | 339.06 | 2744.37 | 0.3 | 56.56 | -25.75 | 62.15 | 335.52 | 4 | Production
Diesel Daily | Diesel Total | +Gain/-Loss | Cntrfg Hrs | Torque and Drag Summary |  |  |  |  | 2927' | 5.1 | 334.5 | 2992.34 | 1.43 | 74.28 | -32.87 | 81.23 | 336.13
|  |  |  | Depth | Torque | Rot. wt. | PU wt. | SO wt. | 3017' | 4.36 | 333.51 | 3012.03 | 0.83 | 80.95 | -36.12 | 88.65 | 335.96 | IADC OP Codes
Mud Product Used Last 24 hours |  |  |  | 2091' | 9 to 10 | 144 | 148 | 140 | 3196' | 2.33 | 338.99 | 3190.69 | 1.44 | 91.04 | -40.1 | 99.48 | 336.23 | 1 | Rig Up and Tear Down
Lime 15, Soda ash 10, Soap sticks 9, MF-55 2, |  |  |  | 2359' | 8 to 11 | 147 | 150 | 142 | 3375' | 1.93 | 336.53 | 3369.58 | 0.22 | 96.98 | -42.26 | 105.79 | 336.45 | 2 | Drill Actual
|  |  |  | 2628' | 8 to 11 | 153 | 158 | 145 | 3554' | 2.02 | 339.74 | 3548.48 | 0.14 | 102.6 | -44.53 | 111.85 | 336.54 | 3 | Reaming
|  |  |  | 2897' | 8 to 11 | 160 | 165 | 155 | 3733' | 1.4 | 323.5 | 3727.38 | 3.09 | 106.39 | -47.22 | 116.4 | 336.06 | 4 | Coring
Drill Pipe Chemical Used Last 24 hours |  |  |  | 3344' | 11 | 166 | 172 | 158 | 4091' | 1.03 | 316.03 | 4085.31 | 0.06 | 113.12 | -51.44 | 124.27 | 335.55 | 5 | Condition Mud and Circulate
|  |  |  | 3970' | 12 | 174 | 175 | 163 | 4271' | 1.05 | 320.03 | 4265.28 | 0.09 | 115.6 | -53.47 | 127.37 | 335.18 | 6 | Trips
[9 empty] | Last Survey Proximity to Plan Line |  |  |  | A/B | 10 B | L/R | 10 L |  | 7 | Lubricate Rig
From | To | Hours | Op Code | Activity for Previous 24 Hours | [13 empty] | 8 | Repair Rig
6:00 | 15:30 | 9.5 | 2.2 | (Intermediate) 12 1/4" hole Rot/Slide f/ 1860' t/ 2986'/ 1126'/ 118.5 FPH/ WOB 20-30/ GPM 750-850/ RPM 55/ MRPM 125-141/ TQ 7-14 | [13 empty] | 9 | Cut Off Drilling Line
15:30 | 16:00 | 0.5 | 2.7 | Rig service | [13 empty] | 10 | Deviation Survey
16:00 | 18:00 | 2 | 2.2 | (Intermediate) 12 1/4" hole Rot/Slide f/ 2986' t/ 3121'/ 135'/ 67.5 FPH/ WOB 20-30/ GPM 750-850/ RPM 55/ MRPM 141/ TQ 7-14 | [13 empty] | 11 | Wireline Logs
18:00 | 3:00 | 9 | 2.2 | (Intermediate) 12 1/4" hole Rot/ Slide f/ 3121' t/ 4150'/ 1029'/ 114.3 FPH/ WOB 20-37/ GPM 840/ RPM 55/ MRPM 139/ TQ 7-14 | [13 empty] | 12 | Run Casing and Cement
3:00 | 3:30 | 0.5 | 2.7 | Rig service | [13 empty] | 13 | Wait on Cement
3:30 | 6:00 | 2.5 | 2.2 | (Intermediate) 12 1/4" hole Rot/ Slide f/ 4150' t/ 4385'/ 235'/ 94 FPH/ WOB 20-37/ GPM 840/ RPM 55/ MRPM 139/ TQ 7-14 (Mudded up @ 4330') | [13 empty] | 14 | Nipple Up BOP
6:00 | [17 empty] | 15 | Test BOP
0:00 | [17 empty] | 16 | Drill Stem Test
0:00 | [17 empty] | 17 | Plug Back
0:00 | [17 empty] | 18 | Squeeze Cement
0:00 | [17 empty] | 19 | Fishing
0:00 | [17 empty] | 20 | Directional Work
0:00 | [17 empty] | 21 | Non Productive Time
0:00 | [17 empty] | 22
0:00 | [17 empty] | 23
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
TOTAL HOURS |  | 24 |  | Drilling Hrs: 23 Fresh water gel tanks 2000 Shaker Screens 1 RRC #
Bit # | Size | Mfg | Type | Part | SN | Jets | In | Out | Ftg | Hrs | ROP | Grade | Gauge | Rsn Pulled | Comments
1 | 17.5 | PDC Logic | KS1963AR |  | 17111528 | 8X16 | 40 | 1177 | 1137 | 20.5 | 55.4634 | 1,1 | In | TD | Surface
2 | 12.25 | Ulterra | CF 616 | U03001 | 39972 | 6 X 16 | 1177 | 4385 | 3208 | 27.25 | 117.7248 |  |  |  | Intermediate
BHA # | Description | [7 empty] | BHA Lngth | Motor Mfg | Size | Bend | Stab OD | Fixed/Adj | Lobes/Stages | RPG | SN
1 | Bit, Bit Sub, Shock Sub, True Fire, 8" DC, IBS, 8" DC, X/O, 5-6" DC's | [7 empty] | 237.43
2 | 12 1/4" bit, Motor #1, 11 3/4" Stab, UBHO, 2-NMDC, 11 3/4" Stab, 6-8" DC's, X/O, 12-6 1/2" DC's, X/O | [7 empty] | 660.53 | Renagade | 9 5/8 | 1.5 | 11.5 | Fixed | 7/8: 4.0 | .166 | RDM 911
|  | size | Wt. | Grade | Conn. | Jts | Length | Jts / Loc | String Volume |  |  |  | Size | Wt/Grade | Bottom | Top | Date Set
Drill Pipe (bottom) |  | 5 | 19.5 | S-135 | 4.5 IF |  |  |  | 68.2 | bbls. | Conductor |  | 20 | 52.78 / B | 50 | 0'
Drill Pipe (middle) |  | 5 | 49.8 | HWDP | 4.5 IF | [5 empty] | Surface Casing |  | 13.375 | 54.50 / J-55 | 1177 | 0'
Drill Pipe (top) |  | 5 | 19.5 | S-135 | 4.5 IF | 84 | 3759.24 | 443 |  |  | Intermediate Csg
Assumed Pump Eff. |  | Pump No. 1 |  | 95% | Pump No. 2 |  | 95% | Slow Pump Rate/Press |  |  | Intermediate 2 Csg
| Type | Liner OD | Length | GPS (100%) | SPM | GPM | Press | Depth | SPM | Pressure | Production Casing
Pump No. 1 | FB-1600 | 6 | 12 | 4.4 | 100 | 418 | 3450 | 4150 | 30 | 200 | Personnel Summary |  |  | Contact Information
Pump No. 2 | FB-1600 | 6 | 12 | 4.4 | 100 | 418 | 3450 | 4150 | 30 | 200 | Rig Crew Days |  | 5 | Foreman Days |  | Richard Hardwick
Surface Rig Spud Date |  | 2018-05-22 | Time | 19:30 | Loads/bbls FW Hauled |  |  | Item | Serial Number |  | Rig Crew Nights |  | 6 | Phone |  | (432)553-6153
Surface Rig Release Date |  | 2018-05-24 | Time | 13:30 | Loads/bbls BW Hauled |  |  | Stab 1 | B&A 8626 |  | Toolpusher |  | 1 | Foreman Nights |  | Randall Blue
Rig Spud Date |  | 2018-06-23 | Time | 9:15 | Loads/bbls Res Hauled |  |  | Stab 2 | B&A 87596 |  | Company Formen |  | 2 | Phone |  | (325)315-3200
Rig Pause Date |  |  | Time |  | Loads Gel Hauled |  | 1 | Stab 3 |  |  | Directional Drillers |  | 2 | Toolpusher |  | Nick Pool
Rig Resume Date |  |  | Time |  | Loads Barite Hauled |  |  | Surv Tool |  |  | MWD |  | 2 | Phone |  | (254) 624-3082
Rig Release Date |  |  | Time |  | Loads OBM Cuttings |  |  | Bit Sub |  |  | Mud Engineer |  |  | Directional Days |  | Wesley Teeter
Incident/Safety Information | [7 empty] | Shock Sub |  |  | Solids Control |  |  | Phone |  | (817) 408-6235
No accidents reported last 24 hours | [7 empty] | Agitator |  |  | Other |  |  | Directional Nights |  | Shane Longmire
[8 empty] | NMDC | DR86229 / DR340115 |  | Total Personnel |  | 18 | Phone |  | (361) 354-4160
Well Name | Gwendolyn #2612 LB |  |  | Date | 2018-06-25 |  | Report # | 5 | Depth | 4385 | Footage | 2525
Op at RT | (Intermediate) Drilling 12 1/4" hole @ 4385' |  |  |  |  | Daily Cost | 46944 |  | Deviation Surveys
Contr/Rig # | Precision Rig 593 |  |  | Total Days | 3.6146 | Total Cost | 368163 |  | MD | Angle | Azimuth | TVD
Bit No. | Size | In | Out | Ftg | Hrs | ROP | Grade | Rsn Pulled | 1942' | 0.86 | 338.02 | 1941.91
1 | 17.5 | 40 | 1177 | 1137 | 20.5 | 55.4634 | 1,1 | TD | 2211' | 4.53 | 342.69 | 2210.58
2 | 12.25 | 1177 | 4385 | 3208 | 27.25 | 117.7248 | 0 | 0 | 2480' | 6.39 | 339.06 | 2478.21
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 2748' | 6.82 | 339.06 | 2744.37
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 2927' | 5.1 | 334.5 | 2992.34
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 3017' | 4.36 | 333.51 | 3012.03
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 3196' | 2.33 | 338.99 | 3190.69
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 3375' | 1.93 | 336.53 | 3369.58
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 3554' | 2.02 | 339.74 | 3548.48
|  | Size | Wt/Grade | Bottom | Top | Date Set | Mud Wt. | 9.5 | 3733' | 1.4 | 323.5 | 3727.38
Conductor |  | 20 | 52.78 / B | 50 | 0' | 0 | Vis | 32 | 4091' | 1.03 | 316.03 | 4085.31
Surface Casing |  | 13.375 | 54.50 / J-55 | 1177 | 0' | 0 | pH | 11 | 4271' | 1.05 | 320.03 | 4265.28
Intermediate Csg |  | 0 | 0 | 0 | 0 | 0 | API WL | 0
Intermediate 2 Csg |  | 0 | 0 | 0 | 0 | 0 | Chlorides | 0
Production Casing |  | 0 | 0 | 0 | 0 | 0 | OWR | 0
Surface Rig Spud Date |  | 2018-05-22 | Time | 19:30 | Rig Pause Date |  | 0 | Time | 0:00
Surface Rig Release Date |  | 2018-05-24 | Time | 13:30 | Rig Resume Date |  | 0 | Time | 0:00
Rig Spud Date |  | 2018-06-23 | Time | 9:15 | Rig Release Date |  | 0 | Time | 0:00

## Report (6)
Well Name | Gwendolyn #2612 LB |  |  | Date | 2018-06-26 |  | Report # | 6 | Depth | 6620 | Footage | 2235 | Planned TD | 8518 | Pad Location | 2-2
Op at RT | (Intermediate) Drilling 12 1/4" hole @ 6620' |  |  |  |  | Daily Cost | 75106 |  | Deviation Surveys
Contr/Rig # | Precision Rig 593 |  |  | Total Days | 4.6146 | Total Cost | 443269 |  | MD | Angle | Azimuth | TVD | DLS | +N/-S | +E/-W | Closure D | Closure A | Hole Section Codes
Mud WT. | Vis | PV | YP | Gels | API WL | pH | Solids | Chlorides | 4450' | 0.33 | 321.33 | 4444.26 | 0.98 | 117.86 | -55.39 | 130.23 | 334.83 | 1 | Surface
9 | 44 | 8 | 12 | 7 / 15 |  | 11 | 2.7 | 44000 | 4629' | 0.1 | 10.47 | 4623.26 | 0.33 | 117.9 | -55.27 | 130.21 | 334.88 | 2 | Intermediate
HTHP | OWR | ES | WPS | LGS | 6 RPM | 3 RPM | Diesel Rate | Water Rate | 4808' | 0.31 | 75.54 | 4802.25 | 0.2 | 118 | -54.79 | 130.1 | 335.09 | 3 | Intermediate 2
[6 empty] | 7 |  |  | 4987' | 0.42 | 99.22 | 4981.25 | 0.15 | 118 | -53.76 | 129.67 | 335.51 | 4 | Production
Diesel Daily | Diesel Total | +Gain/-Loss | Cntrfg Hrs | Torque and Drag Summary |  |  |  |  | 5166' | 0.3 | 68.31 | 5160.25 | 0.2 | 118.06 | -52.55 | 129.22 | 336.01
|  |  |  | Depth | Torque | Rot. wt. | PU wt. | SO wt. | 5435' | 0.13 | 320.22 | 5429.25 | 0.31 | 118.29 | -52.02 | 129.23 | 336.26 | IADC OP Codes
Mud Product Used Last 24 hours |  |  |  | 4509' | 12 to 14 | 185 | 190 | 170 | 5524' | 0.08 | 259.43 | 5518.25 | 0.13 | 118.36 | -52.15 | 129.34 | 336.22 | 1 | Rig Up and Tear Down
Lime 21, Soda ash 45, Hulls 17, Fiber seal 17, Multieseal 12 |  |  |  | 4777' | 8 to12 | 192 | 197 | 188 | 5704' | 0.17 | 240.94 | 5698.25 | 0.08 | 118.12 | -52.45 | 129.25 | 336.06 | 2 | Drill Actual
|  |  |  | 5046' | 8 to 14 | 199 | 207 | 190 | 5972' | 0.23 | 139.13 | 5966.24 | 0.1 | 117.26 | -51.93 | 128.25 | 336.11 | 3 | Reaming
|  |  |  | 5315' | 12 | 204 | 212 | 195 | 6151' | 0.17 | 1.09 | 6145.24 | 0.57 | 116.77 | -51.56 | 127.65 | 336.18 | 4 | Coring
Drill Pipe Chemical Used Last 24 hours |  |  |  | 6121' | 12 | 210 | 219 | 198 | 6330' | 0.6 | 340.55 | 6324.24 | 0.29 | 117.85 | -52.16 | 128.88 | 336.13 | 5 | Condition Mud and Circulate
C202=12 , CL9390=20, CLTD 120=3 |  |  |  | 6300 | 14 | 213 | 221 | 200 | 6509' | 0.36 | 317.95 | 6503.23 | 0.12 | 119 | -52.73 | 130.16 | 336.1 | 6 | Trips
[9 empty] | Last Survey Proximity to Plan Line |  |  |  | A/B | 13 B | L/R | 8 L |  | 7 | Lubricate Rig
From | To | Hours | Op Code | Activity for Previous 24 Hours | [13 empty] | 8 | Repair Rig
6:00 | 15:45 | 9.75 | 2.2 | (Intermediate) 12 1/4" hole Rot/ Slide f/ 4385' t/ 5315'/ 930'/ 95.3 FPH/ WOB 20-40/ GPM 840/ RPM 55/ MRPM 139/ TQ 8-14 | [13 empty] | 9 | Cut Off Drilling Line
15:45 | 16:15 | 0.5 | 2.7 | Rig service & Flow check, Well flowing 18.75 gpm @ 5315' | [13 empty] | 10 | Deviation Survey
16:15 | 18:00 | 1.75 | 2.2 | (Intermediate) 12 1/4" hole Rot/ Slide f/ 5315' t/ 5539'/ 224'/ 128 FPH/ WOB 20-40/ GPM 840/ RPM 55/ MRPM 139/ TQ 8-14 | [13 empty] | 11 | Wireline Logs
18:00 | 23:15 | 5.25 | 2.2 | (Intermediate) 12 1/4" hole Rot/ Slide f/ 5539' t/ 6132'/ 593'/ 112.9 FPH/ WOB 20-40/ GPM 840/ RPM 55/ MRPM 139/ TQ 8-12 | [13 empty] | 12 | Run Casing and Cement
23:15 | 23:45 | 0.5 | 2.7 | Rig service | [13 empty] | 13 | Wait on Cement
23:45 | 6:00 | 6.25 | 2.2 | (Intermediate) 12 1/4" hole Rot/ Slide f/ 6132' t/ 6620'/ 488'/ 78 FPH/ WOB 30-40/ GPM 675-740/ RPM 55/ MRPM 112-124/ TQ 8-14 | [13 empty] | 14 | Nipple Up BOP
6:00 | [17 empty] | 15 | Test BOP
0:00 | [17 empty] | 16 | Drill Stem Test
0:00 | [17 empty] | 17 | Plug Back
0:00 | [17 empty] | 18 | Squeeze Cement
0:00 | [17 empty] | 19 | Fishing
0:00 | [17 empty] | 20 | Directional Work
0:00 | [17 empty] | 21 | Non Productive Time
0:00 | [17 empty] | 22
0:00 | [17 empty] | 23
0:00
0:00
0:00 |  |  |  | Retuns down to 4% @ 6283' for 5 mins
0:00 |  |  |  | Displace hole with gel @ 4330', 8400 strokes mud to surface.
0:00
0:00
0:00
0:00
0:00
0:00
0:00
TOTAL HOURS |  | 24 |  | Drilling Hrs: 23 Fresh water gel tanks 2500 Dumped 1525 bbls Shaker Screens 0 RRC # 132473
Bit # | Size | Mfg | Type | Part | SN | Jets | In | Out | Ftg | Hrs | ROP | Grade | Gauge | Rsn Pulled | Comments
1 | 17.5 | PDC Logic | KS1963AR |  | 17111528 | 8X16 | 40 | 1177 | 1137 | 20.5 | 55.4634 | 1,1 | In | TD | Surface
2 | 12.25 | Ulterra | CF 616 | U03001 | 39972 | 6 X 16 | 1177 | 6620 | 5443 | 50.25 | 108.3184 |  |  |  | Intermediate
BHA # | Description | [7 empty] | BHA Lngth | Motor Mfg | Size | Bend | Stab OD | Fixed/Adj | Lobes/Stages | RPG | SN
1 | Bit, Bit Sub, Shock Sub, True Fire, 8" DC, IBS, 8" DC, X/O, 5-6" DC's | [7 empty] | 237.43
2 | 12 1/4" bit, Motor #1, 11 3/4" Stab, UBHO, 2-NMDC, 11 3/4" Stab, 6-8" DC's, X/O, 12-6 1/2" DC's, X/O | [7 empty] | 660.53 | Renagade | 9 5/8 | 1.5 | 11.5 | Fixed | 7/8: 4.0 | .166 | RDM 911
|  | size | Wt. | Grade | Conn. | Jts | Length | Jts / Loc | String Volume |  |  |  | Size | Wt/Grade | Bottom | Top | Date Set
Drill Pipe (bottom) |  | 5 | 19.5 | S-135 | 4.5 IF |  |  |  | 107.1 | bbls. | Conductor |  | 20 | 52.78 / B | 50 | 0'
Drill Pipe (middle) |  | 5 | 49.8 | HWDP | 4.5 IF | [5 empty] | Surface Casing |  | 13.375 | 54.50 / J-55 | 1177 | 0' | 2018-05-24
Drill Pipe (top) |  | 5 | 19.5 | S-135 | 4.5 IF | 134 | 5997.92 | 443 |  |  | Intermediate Csg
Assumed Pump Eff. |  | Pump No. 1 |  | 95% | Pump No. 2 |  | 95% | Slow Pump Rate/Press |  |  | Intermediate 2 Csg
| Type | Liner OD | Length | GPS (100%) | SPM | GPM | Press | Depth | SPM | Pressure | Production Casing
Pump No. 1 | FB-1600 | 6 | 12 | 4.4 | 80 | 334.4 | 2500 | 6568 | 30 | 270 | Personnel Summary |  |  | Contact Information
Pump No. 2 | FB-1600 | 6 | 12 | 4.4 | 80 | 334.4 | 2500 | 6568 | 30 | 270 | Rig Crew Days |  | 5 | Foreman Days |  | Richard Hardwick
Surface Rig Spud Date |  | 2018-05-22 | Time | 19:30 | Loads/bbls FW Hauled |  |  | Item | Serial Number |  | Rig Crew Nights |  | 6 | Phone |  | (432)553-6153
Surface Rig Release Date |  | 2018-05-24 | Time | 13:30 | Loads/bbls BW Hauled |  |  | Stab 1 | B&A 8626 |  | Toolpusher |  | 1 | Foreman Nights |  | Randall Blue
Rig Spud Date |  | 2018-06-23 | Time | 9:15 | Loads/bbls Res Hauled |  | 3540 | Stab 2 | B&A 87596 |  | Company Formen |  | 2 | Phone |  | (325)315-3200
Rig Pause Date |  |  | Time |  | Loads Gel Hauled |  | 2 | Stab 3 |  |  | Directional Drillers |  | 2 | Toolpusher |  | Nick Pool
Rig Resume Date |  |  | Time |  | Loads Barite Hauled |  |  | Surv Tool |  |  | MWD |  | 2 | Phone |  | (254) 624-3082
Rig Release Date |  |  | Time |  | Loads OBM Cuttings |  |  | Bit Sub |  |  | Mud Engineer |  |  | Directional Days |  | Wesley Teeter
Incident/Safety Information | [7 empty] | Shock Sub |  |  | Solids Control |  |  | Phone |  | (817) 408-6235
No accidents reported last 24 hours | [7 empty] | Agitator |  |  | Other |  |  | Directional Nights |  | Shane Longmire
[8 empty] | NMDC | DR86229 / DR340115 |  | Total Personnel |  | 18 | Phone |  | (361) 354-4160
Well Name | Gwendolyn #2612 LB |  |  | Date | 2018-06-26 |  | Report # | 6 | Depth | 6620 | Footage | 2235
Op at RT | (Intermediate) Drilling 12 1/4" hole @ 6620' |  |  |  |  | Daily Cost | 75106 |  | Deviation Surveys
Contr/Rig # | Precision Rig 593 |  |  | Total Days | 4.6146 | Total Cost | 443269 |  | MD | Angle | Azimuth | TVD
Bit No. | Size | In | Out | Ftg | Hrs | ROP | Grade | Rsn Pulled | 4450' | 0.33 | 321.33 | 4444.26
1 | 17.5 | 40 | 1177 | 1137 | 20.5 | 55.4634 | 1,1 | TD | 4629' | 0.1 | 10.47 | 4623.26
2 | 12.25 | 1177 | 6620 | 5443 | 50.25 | 108.3184 | 0 | 0 | 4808' | 0.31 | 75.54 | 4802.25
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 4987' | 0.42 | 99.22 | 4981.25
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 5166' | 0.3 | 68.31 | 5160.25
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 5435' | 0.13 | 320.22 | 5429.25
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 5524' | 0.08 | 259.43 | 5518.25
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 5704' | 0.17 | 240.94 | 5698.25
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 5972' | 0.23 | 139.13 | 5966.24
|  | Size | Wt/Grade | Bottom | Top | Date Set | Mud Wt. | 9 | 6151' | 0.17 | 1.09 | 6145.24
Conductor |  | 20 | 52.78 / B | 50 | 0' | 0 | Vis | 44 | 6330' | 0.6 | 340.55 | 6324.24
Surface Casing |  | 13.375 | 54.50 / J-55 | 1177 | 0' | 2018-05-24 | pH | 11 | 6509' | 0.36 | 317.95 | 6503.23
Intermediate Csg |  | 0 | 0 | 0 | 0 | 0 | API WL | 0
Intermediate 2 Csg |  | 0 | 0 | 0 | 0 | 0 | Chlorides | 44000
Production Casing |  | 0 | 0 | 0 | 0 | 0 | OWR | 0
Surface Rig Spud Date |  | 2018-05-22 | Time | 19:30 | Rig Pause Date |  | 0 | Time | 0:00
Surface Rig Release Date |  | 2018-05-24 | Time | 13:30 | Rig Resume Date |  | 0 | Time | 0:00
Rig Spud Date |  | 2018-06-23 | Time | 9:15 | Rig Release Date |  | 0 | Time | 0:00

## Report (7)
Well Name | Gwendolyn #2612 LB |  |  | Date | 2018-06-27 |  | Report # | 7 | Depth | 8205 | Footage | 1585 | Planned TD | 8518 | Pad Location | 2-2
Op at RT | (Intermediate) Drilling 12 1/4" hole @ 8205' |  |  |  |  | Daily Cost | 58139 |  | Deviation Surveys
Contr/Rig # | Precision Rig 593 |  |  | Total Days | 5.6146 | Total Cost | 501408 |  | MD | Angle | Azimuth | TVD | DLS | +N/-S | +E/-W | Closure D | Closure A | Hole Section Codes
Mud WT. | Vis | PV | YP | Gels | API WL | pH | Solids | Chlorides | 6599' | 0.07 | 336.68 | 6593.23 | 0.33 | 119.26 | -52.94 | 130.48 | 336.06 | 1 | Surface
9 | 40 | 7 | 10 | 6 / 11 |  | 10 | 3 | 28000 | 6778' | 0.11 | 62.53 | 6772.23 | 0.08 | 119.55 | -52.75 | 130.67 | 336.19 | 2 | Intermediate
HTHP | OWR | ES | WPS | LGS | 6 RPM | 3 RPM | Diesel Rate | Water Rate | 6957' | 0.33 | 95.9 | 6951.23 | 0.15 | 119.54 | -52.11 | 130.4 | 336.45 | 3 | Intermediate 2
[6 empty] | 6 |  |  | 7137' | 0.33 | 59.79 | 7131.23 | 0.14 | 120.1 | -51.18 | 130.55 | 336.92 | 4 | Production
Diesel Daily | Diesel Total | +Gain/-Loss | Cntrfg Hrs | Torque and Drag Summary |  |  |  |  | 7316' | 1.16 | 84.5 | 7310.21 | 0.6 | 120.69 | -49.06 | 130.28 | 337.88
|  |  |  | Depth | Torque | Rot. wt. | PU wt. | SO wt. | 7405' | 1.05 | 79.54 | 7399.19 | 0.16 | 120.93 | -47.36 | 129.87 | 338.61 | IADC OP Codes
Mud Product Used Last 24 hours |  |  |  | 6658' | 13 to 14 | 228 | 235 | 215 | 7495' | 1 | 88.43 | 7489.18 | 0.19 | 121.1 | -45.76 | 129.46 | 339.3 | 1 | Rig Up and Tear Down
Lime 27, Soda ash 40, Hulls 32, Fiber seal 32, Multieseal 32 |  |  |  | 6927' | 13 | 233 | 240 | 220 | 7674' | 1.19 | 69.06 | 7668.15 | 0.37 | 121.64 | -42.3 | 128.88 | 340.7 | 2 | Drill Actual
|  |  |  | 7285' | 13 | 240 | 244 | 225 | 7763' | 1.34 | 70.8 | 7757.13 | 0.17 | 122.31 | -40.75 | 128.92 | 341.57 | 3 | Reaming
|  |  |  | 7783' | 15 | 243 | 254 | 229 | 7942' | 1..68 | 78.4 | 7936.06 | 0.12 | 123.57 | -35.79 | 128.65 | 343.85 | 4 | Coring
Drill Pipe Chemical Used Last 24 hours |  |  |  | 8001' | 14 to 16 | 245 | 255 | 229 | 8032' | 1.65 | 75.67 | 8026.02 | 0.09 | 124.16 | -33.24 | 128.53 | 345.01 | 5 | Condition Mud and Circulate
C202=6 , CL9390=20, CLTD 120=3 | [8 empty] | 8121' | 1.33 | 72.75 | 8114.99 | 0.37 | 124.78 | -31.01 | 128.58 | 346.04 | 6 | Trips
[9 empty] | Last Survey Proximity to Plan Line |  |  |  | A/B | 14 B | L/R | 13 R |  | 7 | Lubricate Rig
From | To | Hours | Op Code | Activity for Previous 24 Hours | [13 empty] | 8 | Repair Rig
6:00 | 16:00 | 10 | 2.2 | (Intermediate) 12 1/4" hole Rot/ Slide f/ 6620' t/ 7375'/ 755'/ 75.5 FPH/ WOB 30-40/ GPM 675-700/ RPM 55/ MRPM 112-116/ TQ 8-22 | [13 empty] | 9 | Cut Off Drilling Line
16:00 | 16:30 | 0.5 | 2.7 | Rig Service, Clean rad on gen #2 | [13 empty] | 10 | Deviation Survey
16:30 | 17:00 | 0.5 | 2.2 | (Intermediate) 12 1/4" hole Rot/ Slide f/ 7375'' t/ 7395'/ 20'/ 40 FPH/ WOB 30-40/ GPM 700/ RPM 55/ MRPM 116/ TQ 8-22 | [13 empty] | 11 | Wireline Logs
17:00 | 17:15 | 0.25 | 2.5 | Circulate and change liner gasket in pump #2 | [13 empty] | 12 | Run Casing and Cement
17:15 | 18:00 | 0.75 | 2.2 | (Intermediate) 12 1/4" hole Rot/Slide f/ 7395' t/ 7445'/ 50'/ 66.7 FPH/ WOB 30-40/ GPM 700/ RPM 55/ MRPM 116/ TQ 8-22 | [13 empty] | 13 | Wait on Cement
18:00 | 18:30 | 0.5 | 2.2 | (Intermediate) 12 1/4" hole Rot/ Slide f/ 7445' t/ 7484'/ 39'/ 78 FPH/ WOB 30-40/ GPM 700/ RPM 55/ MRPM 116/ TQ 8-22 | [13 empty] | 14 | Nipple Up BOP
18:30 | 19:15 | 0.75 | 2.5 | Circulate and change liner in pump #1 | [13 empty] | 15 | Test BOP
19:15 | 1:15 | 6 | 2.2 | (Intermediate) 12 1/4" hole Rot/ Slide f/ 7484' t/ 8001'/ 517'/ 86.2 FPH/ WOB 30-40/ GPM 700/ RPM 55/ MRPM 116/ TQ 8-18 | [13 empty] | 16 | Drill Stem Test
1:15 | 3:00 | 1.75 | 2.2 | (Intermediate) 12 1/4" hole Rot/ Slide f/ 8001' t/ 8091'/ 90'/ 51.4 FPH/ WOB 30-40/ GPM 600/ RPM 55/ MRPM 100/ TQ 8-22 | [13 empty] | 17 | Plug Back
3:00 | 3:30 | 0.5 | 2.7 | Rig Service. | [13 empty] | 18 | Squeeze Cement
3:30 | 6:00 | 2.5 | 2.2 | (Intermediate) 12 1/4" hole Rot/ Slide f/ 8091' t/ 8205'/ 114'/ 45.6 FPH/ WOB 30-40/ GPM 600/ RPM 55/ MRPM 100/ TQ 8-22 | [13 empty] | 19 | Fishing
6:00 | [17 empty] | 20 | Directional Work
0:00 | [17 empty] | 21 | Non Productive Time
0:00 | [17 empty] | 22
0:00 | [17 empty] | 23
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00 |  |  |  | REC: 118 jts of 9 5/8" Bare casing & 91 jts of Ryte-wrap casing from Master Tubulars
0:00 |  |  |  | Art's casing inspection, All casing was Good
0:00 |  |  |  | Rec: Packer/DV and float equipment from Blackhawk
TOTAL HOURS |  | 24 |  | Drilling Hrs: 22 Fresh water gel tanks 2500 Dumped 1550 bbls Shaker Screens 0 RRC # 132473
Bit # | Size | Mfg | Type | Part | SN | Jets | In | Out | Ftg | Hrs | ROP | Grade | Gauge | Rsn Pulled | Comments
1 | 17.5 | PDC Logic | KS1963AR |  | 17111528 | 8X16 | 40 | 1177 | 1137 | 20.5 | 55.4634 | 1,1 | In | TD | Surface
2 | 12.25 | Ulterra | CF 616 | U03001 | 39972 | 6 X 16 | 1177 | 8205 | 7028 | 72.25 | 97.2734 |  |  |  | Intermediate
BHA # | Description | [7 empty] | BHA Lngth | Motor Mfg | Size | Bend | Stab OD | Fixed/Adj | Lobes/Stages | RPG | SN
1 | Bit, Bit Sub, Shock Sub, True Fire, 8" DC, IBS, 8" DC, X/O, 5-6" DC's | [7 empty] | 237.43
2 | 12 1/4" bit, Motor #1, 11 3/4" Stab, UBHO, 2-NMDC, 11 3/4" Stab, 6-8" DC's, X/O, 12-6 1/2" DC's, X/O | [7 empty] | 660.53 | Renagade | 9 5/8 | 1.5 | 11.5 | Fixed | 7/8: 4.0 | .166 | RDM 911
|  | size | Wt. | Grade | Conn. | Jts | Length | Jts / Loc | String Volume |  |  |  | Size | Wt/Grade | Bottom | Top | Date Set
Drill Pipe (bottom) |  | 5 | 19.5 | S-135 | 4.5 IF |  |  |  | 134.9 | bbls. | Conductor |  | 20 | 52.78 / B | 50 | 0'
Drill Pipe (middle) |  | 5 | 49.8 | HWDP | 4.5 IF | [5 empty] | Surface Casing |  | 13.375 | 54.50 / J-55 | 1177 | 0' | 2018-05-24
Drill Pipe (top) |  | 5 | 19.5 | S-135 | 4.5 IF | 170 | 7642.78 | 443 |  |  | Intermediate Csg
Assumed Pump Eff. |  | Pump No. 1 |  | 95% | Pump No. 2 |  | 95% | Slow Pump Rate/Press |  |  | Intermediate 2 Csg
| Type | Liner OD | Length | GPS (100%) | SPM | GPM | Press | Depth | SPM | Pressure | Production Casing
Pump No. 1 | FB-1600 | 6 | 12 | 4.4 | 72 | 300.96 | 2500 | 8091 | 30 | 240 | Personnel Summary |  |  | Contact Information
Pump No. 2 | FB-1600 | 6 | 12 | 4.4 | 72 | 300.96 | 2500 | 8091 | 30 | 250 | Rig Crew Days |  | 6 | Foreman Days |  | Richard Hardwick
Surface Rig Spud Date |  | 2018-05-22 | Time | 19:30 | Loads/bbls FW Hauled |  |  | Item | Serial Number |  | Rig Crew Nights |  | 6 | Phone |  | (432)553-6153
Surface Rig Release Date |  | 2018-05-24 | Time | 13:30 | Loads/bbls BW Hauled |  |  | Stab 1 | B&A 8626 |  | Toolpusher |  | 1 | Foreman Nights |  | Randall Blue
Rig Spud Date |  | 2018-06-23 | Time | 9:15 | Loads/bbls Res Hauled |  | 2240 | Stab 2 | B&A 87596 |  | Company Formen |  | 2 | Phone |  | (325)315-3200
Rig Pause Date |  |  | Time |  | Loads Gel Hauled |  | 1 | Stab 3 |  |  | Directional Drillers |  | 2 | Toolpusher |  | Doug Stovall
Rig Resume Date |  |  | Time |  | Loads Barite Hauled |  |  | Surv Tool |  |  | MWD |  | 2 | Phone |  | (940) 297-7726
Rig Release Date |  |  | Time |  | Loads OBM Cuttings |  |  | Bit Sub |  |  | Mud Engineer |  |  | Directional Days |  | Wesley Teeter
Incident/Safety Information | [7 empty] | Shock Sub |  |  | Solids Control |  |  | Phone |  | (817) 408-6235
No accidents reported last 24 hours | [7 empty] | Agitator |  |  | Other |  |  | Directional Nights |  | Shane Longmire
[8 empty] | NMDC | DR86229 / DR340115 |  | Total Personnel |  | 19 | Phone |  | (361) 354-4160
Well Name | Gwendolyn #2612 LB |  |  | Date | 2018-06-27 |  | Report # | 7 | Depth | 8205 | Footage | 1585
Op at RT | (Intermediate) Drilling 12 1/4" hole @ 8205' |  |  |  |  | Daily Cost | 58139 |  | Deviation Surveys
Contr/Rig # | Precision Rig 593 |  |  | Total Days | 5.6146 | Total Cost | 501408 |  | MD | Angle | Azimuth | TVD
Bit No. | Size | In | Out | Ftg | Hrs | ROP | Grade | Rsn Pulled | 6599' | 0.07 | 336.68 | 6593.23
1 | 17.5 | 40 | 1177 | 1137 | 20.5 | 55.4634 | 1,1 | TD | 6778' | 0.11 | 62.53 | 6772.23
2 | 12.25 | 1177 | 8205 | 7028 | 72.25 | 97.2734 | 0 | 0 | 6957' | 0.33 | 95.9 | 6951.23
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 7137' | 0.33 | 59.79 | 7131.23
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 7316' | 1.16 | 84.5 | 7310.21
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 7405' | 1.05 | 79.54 | 7399.19
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 7495' | 1 | 88.43 | 7489.18
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 7674' | 1.19 | 69.06 | 7668.15
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 7763' | 1.34 | 70.8 | 7757.13
|  | Size | Wt/Grade | Bottom | Top | Date Set | Mud Wt. | 9 | 7942' | 1..68 | 78.4 | 7936.06
Conductor |  | 20 | 52.78 / B | 50 | 0' | 0 | Vis | 40 | 8032' | 1.65 | 75.67 | 8026.02
Surface Casing |  | 13.375 | 54.50 / J-55 | 1177 | 0' | 2018-05-24 | pH | 10 | 8121' | 1.33 | 72.75 | 8114.99
Intermediate Csg |  | 0 | 0 | 0 | 0 | 0 | API WL | 0
Intermediate 2 Csg |  | 0 | 0 | 0 | 0 | 0 | Chlorides | 28000
Production Casing |  | 0 | 0 | 0 | 0 | 0 | OWR | 0
Surface Rig Spud Date |  | 2018-05-22 | Time | 19:30 | Rig Pause Date |  | 0 | Time | 0:00
Surface Rig Release Date |  | 2018-05-24 | Time | 13:30 | Rig Resume Date |  | 0 | Time | 0:00
Rig Spud Date |  | 2018-06-23 | Time | 9:15 | Rig Release Date |  | 0 | Time | 0:00

## Report (8)
Well Name | Gwendolyn #2612 LB |  |  | Date | 2018-06-28 |  | Report # | 8 | Depth | 8538 | Footage | 333 | Planned TD | 8518 | Pad Location | 2-2
Op at RT | Circulate 9 5/8 casing @ 2140' |  |  |  |  | Daily Cost | 63343 |  | Deviation Surveys
Contr/Rig # | Precision Rig 593 |  |  | Total Days | 6.6146 | Total Cost | 564751 |  | MD | Angle | Azimuth | TVD | DLS | +N/-S | +E/-W | Closure D | Closure A | Hole Section Codes
Mud WT. | Vis | PV | YP | Gels | API WL | pH | Solids | Chlorides | 8211' | 1.46 | 69.27 | 8204..96 | 0.17 | 125.49 | -28.94 | 128.79 | 347.01 | 1 | Surface
8.9 | 40 | 6 | 9 | 4 / 8 |  | 10 | 2.6 | 40000 | 8300' | 1.94 | 64.38 | 8293.92 | 0.56 | 126.55 | -26.53 | 129.3 | 348.16 | 2 | Intermediate
HTHP | OWR | ES | WPS | LGS | 6 RPM | 3 RPM | Diesel Rate | Water Rate | 8390' | 2.33 | 67.62 | 8383.86 | 0.45 | 127.9 | -23.46 | 130.04 | 349.61 | 3 | Intermediate 2
[6 empty] | 4 |  |  | 8479' | 2.3 | 62.92 | 8472.79 | 0.22 | 129.4 | -20.2 | 130.97 | 351.13 | 4 | Production
Diesel Daily | Diesel Total | +Gain/-Loss | Cntrfg Hrs | Torque and Drag Summary | [8 empty] | 0
|  |  |  | Depth | Torque | Rot. wt. | PU wt. | SO wt. | [9 empty] | IADC OP Codes
Mud Product Used Last 24 hours |  |  |  | 8270' | 12 to 14 | 255 | 260 | 240 | [9 empty] | 1 | Rig Up and Tear Down
Lime 11, Soda ash 25, Hulls 13, Fiber seal 13, Multieseal 13, Starch 100 | [17 empty] | 2 | Drill Actual
[18 empty] | 3 | Reaming
[18 empty] | 4 | Coring
Drill Pipe Chemical Used Last 24 hours | [17 empty] | 5 | Condition Mud and Circulate
C202=6 , CL9390=20, CLTD 120=3 | [17 empty] | 6 | Trips
[9 empty] | Last Survey Proximity to Plan Line |  |  |  | A/B | 13 B | L/R | 23 R |  | 7 | Lubricate Rig
From | To | Hours | Op Code | Activity for Previous 24 Hours | [13 empty] | 8 | Repair Rig
6:00 | 14:30 | 8.5 | 2.2 | (Intermediate) 12 1/4" hole Rot/ Slide f/ 8205' t/ 8538'/ 333'/ 39.1 FPH/ WOB 30-40/ GPM 600/ RPM 55/ MRPM 100/ TQ 8-22 | [13 empty] | 9 | Cut Off Drilling Line
14:30 | 18:30 | 4 | 2.5 | Pump 2-40 bbl sweeps and circulate 3 bottoms up 31,000 strks, flow check off bottom 43 gpm | [13 empty] | 10 | Deviation Survey
18:30 | 22:00 | 3.5 | 2.6 | T.O.O.H w/ drill pipe f/ 8538' t/ 1177' flow check @ shoe 30 gpm | [13 empty] | 11 | Wireline Logs
22:00 | 22:15 | 0.25 | 2.5 | Circulate bottoms up @ the shoe | [13 empty] | 12 | Run Casing and Cement
22:15 | 22:45 | 0.5 | 2.6 | T.O.O.H w/ drill pipe f/ 1177' t/ 660' | [13 empty] | 13 | Wait on Cement
22:45 | 24:00 | 1.25 | 2.6 | T.O.O.H w/ bha stand 2 stds of 6": in derrick and lay down the rest of drill collars | [13 empty] | 14 | Nipple Up BOP
24:00 | 24:45 | 0.75 | 2.20. | Break and lay down directional tools and bit flow out of the hole 25 gpm | [13 empty] | 15 | Test BOP
24:45 | 1:00 | 0.25 | 2.21 | Pull wear bushing | [13 empty] | 16 | Drill Stem Test
1:00 | 2:00 | 1 | 2.21 | Rig up ext bails, make up crt, rig up elevators and dry fit landing joint | [13 empty] | 17 | Plug Back
2:00 | 2:45 | 0.75 | 2.12 | PJSM. Rig up casing crew | [13 empty] | 18 | Squeeze Cement
2:45 | 5:45 | 3 | 2.12 | Make shoe track, Run 9 5/8" casing f/ 0' t/ 2140' | [13 empty] | 19 | Fishing
5:45 | 6:00 | 0.25 | 2.12 | Circulate black water @ 2140' 100 ppm H2S at flowline | [13 empty] | 20 | Directional Work
6:00 | [17 empty] | 21 | Non Productive Time
0:00 | [17 empty] | 22
0:00 | [17 empty] | 23
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00 |  |  |  | Flow off bottom 43 gpm, @ shoe 30 gpm, out of hole 25 gpm
0:00 |  |  |  | RRC contacted @ 19:52 Linda, Operator #8
TOTAL HOURS |  | 24 |  | Drilling Hrs: 8.50 Fresh water gel tanks 2500 Dumped 450 bbls Shaker Screens 0 RRC # 132473
Bit # | Size | Mfg | Type | Part | SN | Jets | In | Out | Ftg | Hrs | ROP | Grade | Gauge | Rsn Pulled | Comments
1 | 17.5 | PDC Logic | KS1963AR |  | 17111528 | 8X16 | 40 | 1177 | 1137 | 20.5 | 55.4634 | 1,1 | In | TD | Surface
2 | 12.25 | Ulterra | CF616M | U03001 | 39972 | 6 X 16 | 1177 | 8538 | 7361 | 80.75 | 91.1579 | 4,4 | In | TD | Intermediate
BHA # | Description | [7 empty] | BHA Lngth | Motor Mfg | Size | Bend | Stab OD | Fixed/Adj | Lobes/Stages | RPG | SN
1 | Bit, Bit Sub, Shock Sub, True Fire, 8" DC, IBS, 8" DC, X/O, 5-6" DC's | [7 empty] | 237.43
2 | 12 1/4" bit, Motor #1, 11 3/4" Stab, UBHO, 2-NMDC, 11 3/4" Stab, 6-8" DC's, X/O, 12-6 1/2" DC's, X/O | [7 empty] | 660.53 | Renegade | 9 5/8 | 1.5 | 11.5 | Fixed | 7/8: 4.0 | .166 | RDM 911
|  | size | Wt. | Grade | Conn. | Jts | Length | Jts / Loc | String Volume |  |  |  | Size | Wt/Grade | Bottom | Top | Date Set
Drill Pipe (bottom) |  | 5 | 19.5 | S-135 | 4.5 IF |  |  |  | 137.3 | bbls. | Conductor |  | 20 | 52.78 / B | 50 | 0'
Drill Pipe (middle) |  | 5 | 49.8 | HWDP | 4.5 IF | [5 empty] | Surface Casing |  | 13.375 | 54.50 / J-55 | 1177 | 0' | 2018-05-24
Drill Pipe (top) |  | 5 | 19.5 | S-135 | 4.5 IF | 176 | 7878.42 | 443 |  |  | Intermediate Csg
Assumed Pump Eff. |  | Pump No. 1 |  | 95% | Pump No. 2 |  | 95% | Slow Pump Rate/Press |  |  | Intermediate 2 Csg
| Type | Liner OD | Length | GPS (100%) | SPM | GPM | Press | Depth | SPM | Pressure | Production Casing
Pump No. 1 | FB-1600 | 6 | 12 | 4.4 | 72 | 300.96 | 2542 | 8091 | 30 | 240 | Personnel Summary |  |  | Contact Information
Pump No. 2 | FB-1600 | 6 | 12 | 4.4 | 72 | 300.96 | 2542 | 8091 | 30 | 250 | Rig Crew Days |  | 6 | Foreman Days |  | Richard Hardwick
Surface Rig Spud Date |  | 2018-05-22 | Time | 19:30 | Loads/bbls FW Hauled |  |  | Item | Serial Number |  | Rig Crew Nights |  | 6 | Phone |  | (432)553-6153
Surface Rig Release Date |  | 2018-05-24 | Time | 13:30 | Loads/bbls BW Hauled |  |  | Stab 1 | B&A 8626 |  | Toolpusher |  | 1 | Foreman Nights |  | Randall Blue
Rig Spud Date |  | 2018-06-23 | Time | 9:15 | Loads/bbls Res Hauled |  | 14 / 1760 | Stab 2 | B&A 87596 |  | Company Formen |  | 2 | Phone |  | (325)315-3200
Rig Pause Date |  |  | Time |  | Loads Gel Hauled |  | 1 | Stab 3 |  |  | Directional Drillers |  | 2 | Toolpusher |  | Doug Stovall
Rig Resume Date |  |  | Time |  | Loads Barite Hauled |  |  | Surv Tool |  |  | MWD |  | 2 | Phone |  | (940) 297-7726
Rig Release Date |  |  | Time |  | Loads OBM Cuttings |  |  | Bit Sub |  |  | Mud Engineer |  |  | Directional Days |  | Wesley Teeter
Incident/Safety Information | [7 empty] | Shock Sub |  |  | Solids Control |  |  | Phone |  | (817) 408-6235
No accidents reported last 24 hours | [7 empty] | Agitator |  |  | Other |  | 6 | Directional Nights |  | Shane Longmire
[8 empty] | NMDC | DR86229 / DR340115 |  | Total Personnel |  | 25 | Phone |  | (361) 354-4160
Well Name | Gwendolyn #2612 LB |  |  | Date | 2018-06-28 |  | Report # | 8 | Depth | 8538 | Footage | 333
Op at RT | Circulate 9 5/8 casing @ 2140' |  |  |  |  | Daily Cost | 63343 |  | Deviation Surveys
Contr/Rig # | Precision Rig 593 |  |  | Total Days | 6.6146 | Total Cost | 564751 |  | MD | Angle | Azimuth | TVD
Bit No. | Size | In | Out | Ftg | Hrs | ROP | Grade | Rsn Pulled | 8211' | 1.46 | 69.27 | 8204..96
1 | 17.5 | 40 | 1177 | 1137 | 20.5 | 55.4634 | 1,1 | TD | 8300' | 1.94 | 64.38 | 8293.92
2 | 12.25 | 1177 | 8538 | 7361 | 80.75 | 91.1579 | 4,4 | TD | 8390' | 2.33 | 67.62 | 8383.86
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 8479' | 2.3 | 62.92 | 8472.79
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Size | Wt/Grade | Bottom | Top | Date Set | Mud Wt. | 8.9 | 0 | 0 | 0 | 0
Conductor |  | 20 | 52.78 / B | 50 | 0' | 0 | Vis | 40 | 0 | 0 | 0 | 0
Surface Casing |  | 13.375 | 54.50 / J-55 | 1177 | 0' | 2018-05-24 | pH | 10 | 0 | 0 | 0 | 0
Intermediate Csg |  | 0 | 0 | 0 | 0 | 0 | API WL | 0
Intermediate 2 Csg |  | 0 | 0 | 0 | 0 | 0 | Chlorides | 40000
Production Casing |  | 0 | 0 | 0 | 0 | 0 | OWR | 0
Surface Rig Spud Date |  | 2018-05-22 | Time | 19:30 | Rig Pause Date |  | 0 | Time | 0:00
Surface Rig Release Date |  | 2018-05-24 | Time | 13:30 | Rig Resume Date |  | 0 | Time | 0:00
Rig Spud Date |  | 2018-06-23 | Time | 9:15 | Rig Release Date |  | 0 | Time | 0:00

## Report (9)
Well Name | Gwendolyn #2612 LB |  |  | Date | 2018-06-29 |  | Report # | 9 | Depth | 8538 | Footage | 333 | Planned TD | 8518 | Pad Location | 2-2
Op at RT | Cement 2nd stage |  |  |  |  | Daily Cost | 366808 |  | Deviation Surveys
Contr/Rig # | Precision Rig 593 |  |  | Total Days | 7.6146 | Total Cost | 931559 |  | MD | Angle | Azimuth | TVD | DLS | +N/-S | +E/-W | Closure D | Closure A | Hole Section Codes
Mud WT. | Vis | PV | YP | Gels | API WL | pH | Solids | Chlorides | 8479' | 2.3 | 62.92 | 8472.79 | 0.22 | 129.4 | -20.2 | 130.97 | 351.13 | 1 | Surface
8.9 | 40 | 6 | 9 | 4 / 8 |  | 10 | 2.6 | 40000 | [9 empty] | 2 | Intermediate
HTHP | OWR | ES | WPS | LGS | 6 RPM | 3 RPM | Diesel Rate | Water Rate | [9 empty] | 3 | Intermediate 2
[6 empty] | 4 | [11 empty] | 4 | Production
Diesel Daily | Diesel Total | +Gain/-Loss | Cntrfg Hrs | Torque and Drag Summary | [8 empty] | 0
|  |  |  | Depth | Torque | Rot. wt. | PU wt. | SO wt. | [9 empty] | IADC OP Codes
Mud Product Used Last 24 hours |  |  |  | 8270' | 12 to 14 | 255 | 260 | 240 | [9 empty] | 1 | Rig Up and Tear Down
Lime 11, Soda ash 25, Hulls 13, Fiber seal 13, Multieseal 13, Starch 100 | [17 empty] | 2 | Drill Actual
[18 empty] | 3 | Reaming
[18 empty] | 4 | Coring
Drill Pipe Chemical Used Last 24 hours | [17 empty] | 5 | Condition Mud and Circulate
[18 empty] | 6 | Trips
[9 empty] | Last Survey Proximity to Plan Line |  |  |  | A/B | 13 B | L/R | 23 R |  | 7 | Lubricate Rig
From | To | Hours | Op Code | Activity for Previous 24 Hours | [13 empty] | 8 | Repair Rig
6:00 | 7:15 | 1.25 | 2.12 | Circulate black water @ 2140' Dump 400 bbls black water to pit | [13 empty] | 9 | Cut Off Drilling Line
7:15 | 10:00 | 2.75 | 2.12 | Run 9 5/8" casing f/ 2140' t/ 4365' | [13 empty] | 10 | Deviation Survey
10:00 | 12:30 | 2.5 | 2.12 | Swab for returns, Regained circulation @ 4365', Dump 570 bbls black water to pit | [13 empty] | 11 | Wireline Logs
12:30 | 14:45 | 2.25 | 2.12 | Run 9 5/8" casing f/ 4365' t/ 7000' | [13 empty] | 12 | Run Casing and Cement
14:45 | 17:30 | 2.75 | 2.12 | Circulate @ 7000' with full returns, Dump 690 bbls of black water to pit | [13 empty] | 13 | Wait on Cement
17:30 | 19:00 | 1.5 | 2.12 | Run 9 5/8' casing f/ 7000' t/ 8515' | [13 empty] | 14 | Nipple Up BOP
19:00 | 21:45 | 2.75 | 2.12 | Circulate @ 8515' with full returns. Circulated 865 bbls of black water to reserve pit, 10400 strks | [13 empty] | 15 | Test BOP
21:45 | 22:00 | 0.25 | 2.12 | PJSM, Rig up cementers & test lines | [13 empty] | 16 | Drill Stem Test
22:00 | 2:00 | 4 | 2.12 | Pump 50 FW, 40 PRO M, 5 FW and Cement 1st stage per prog. Plug down @ 1:30. Circulated 1038 bbls of blackwater to reserve during cement job | [13 empty] | 17 | Plug Back
2:00 | 3:00 | 1 | 2.12 | Drop opening device and freefall for 30 mins. Open DV Tool w/ 720 psi | [13 empty] | 18 | Squeeze Cement
3:00 | 5:30 | 2.5 | 2.12 | Circulating thru dv tool. Circulated 616 bbls of blackwater to reserve pit | [13 empty] | 19 | Fishing
5:30 | 6:00 | 0.5 | 2.12 | Pump 50 bbls fresh water and cement 2nd stage per prog. | [13 empty] | 20 | Directional Work
6:00 | [17 empty] | 21 | Non Productive Time
0:00 | [17 empty] | 22
0:00 | [17 empty] | 23
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00 |  |  |  | Flow off bottom 43 gpm, @ shoe 30 gpm, out of hole 25 gpm
0:00 |  |  |  | RRC contacted @ 19:52 Linda, Operator #8
TOTAL HOURS |  | 24 |  | Drilling Hrs: Fresh water gel tanks 500 Shaker Screens 0 RRC # 132473
Bit # | Size | Mfg | Type | Part | SN | Jets | In | Out | Ftg | Hrs | ROP | Grade | Gauge | Rsn Pulled | Comments
1 | 17.5 | PDC Logic | KS1963AR |  | 17111528 | 8X16 | 40 | 1177 | 1137 | 20.5 | 55.4634 | 1,1 | In | TD | Surface
2 | 12.25 | Ulterra | CF616M | U03001 | 39972 | 6 X 16 | 1177 | 8538 | 7361 | 80.75 | 91.1579 | 4,4 | In | TD | Intermediate
BHA # | Description | [7 empty] | BHA Lngth | Motor Mfg | Size | Bend | Stab OD | Fixed/Adj | Lobes/Stages | RPG | SN
1 | Bit, Bit Sub, Shock Sub, True Fire, 8" DC, IBS, 8" DC, X/O, 5-6" DC's | [7 empty] | 237.43
2 | 12 1/4" bit, Motor #1, 11 3/4" Stab, UBHO, 2-NMDC, 11 3/4" Stab, 6-8" DC's, X/O, 12-6 1/2" DC's, X/O | [7 empty] | 660.53 | Renegade | 9 5/8 | 1.5 | 11.5 | Fixed | 7/8: 4.0 | .166 | RDM 911
|  | size | Wt. | Grade | Conn. | Jts | Length | Jts / Loc | String Volume |  |  |  | Size | Wt/Grade | Bottom | Top | Date Set
Drill Pipe (bottom) |  | 5 | 19.5 | S-135 | 4.5 IF |  |  |  | 137.3 | bbls. | Conductor |  | 20 | 52.78 / B | 50 | 0'
Drill Pipe (middle) |  | 5 | 49.8 | HWDP | 4.5 IF | [5 empty] | Surface Casing |  | 13.375 | 54.50 / J-55 | 1177 | 0' | 2018-05-24
Drill Pipe (top) |  | 5 | 19.5 | S-135 | 4.5 IF | 176 | 7878.42 | 443 |  |  | Intermediate Csg
Assumed Pump Eff. |  | Pump No. 1 |  | 95% | Pump No. 2 |  | 95% | Slow Pump Rate/Press |  |  | Intermediate 2 Csg
| Type | Liner OD | Length | GPS (100%) | SPM | GPM | Press | Depth | SPM | Pressure | Production Casing
Pump No. 1 | FB-1600 | 6 | 12 | 4.4 | 72 | 300.96 | 2542 | 8091 | 30 | 240 | Personnel Summary |  |  | Contact Information
Pump No. 2 | FB-1600 | 6 | 12 | 4.4 | 72 | 300.96 | 2542 | 8091 | 30 | 250 | Rig Crew Days |  | 6 | Foreman Days |  | Richard Hardwick
Surface Rig Spud Date |  | 2018-05-22 | Time | 19:30 | Loads/bbls FW Hauled |  |  | Item | Serial Number |  | Rig Crew Nights |  | 6 | Phone |  | (432)553-6153
Surface Rig Release Date |  | 2018-05-24 | Time | 13:30 | Loads/bbls BW Hauled |  |  | Stab 1 | B&A 8626 |  | Toolpusher |  | 1 | Foreman Nights |  | Randall Blue
Rig Spud Date |  | 2018-06-23 | Time | 9:15 | Loads/bbls Res Hauled |  |  | Stab 2 | B&A 87596 |  | Company Formen |  | 2 | Phone |  | (325)315-3200
Rig Pause Date |  |  | Time |  | Loads Gel Hauled |  |  | Stab 3 |  |  | Directional Drillers |  | 2 | Toolpusher |  | Doug Stovall
Rig Resume Date |  |  | Time |  | Loads Barite Hauled |  |  | Surv Tool |  |  | MWD |  | 2 | Phone |  | (940) 297-7726
Rig Release Date |  |  | Time |  | Loads OBM Cuttings |  |  | Bit Sub |  |  | Mud Engineer |  |  | Directional Days |  | Wesley Teeter
Incident/Safety Information | [7 empty] | Shock Sub |  |  | Solids Control |  |  | Phone |  | (817) 408-6235
No accidents reported last 24 hours | [7 empty] | Agitator |  |  | Other |  | 6 | Directional Nights |  | Shane Longmire
[8 empty] | NMDC | DR86229 / DR340115 |  | Total Personnel |  | 25 | Phone |  | (361) 354-4160
Well Name | Gwendolyn #2612 LB |  |  | Date | 2018-06-29 |  | Report # | 9 | Depth | 8538 | Footage | 333
Op at RT | Cement 2nd stage |  |  |  |  | Daily Cost | 366808 |  | Deviation Surveys
Contr/Rig # | Precision Rig 593 |  |  | Total Days | 7.6146 | Total Cost | 931559 |  | MD | Angle | Azimuth | TVD
Bit No. | Size | In | Out | Ftg | Hrs | ROP | Grade | Rsn Pulled | 8479' | 2.3 | 62.92 | 8472.79
1 | 17.5 | 40 | 1177 | 1137 | 20.5 | 55.4634 | 1,1 | TD | 0 | 0 | 0 | 0
2 | 12.25 | 1177 | 8538 | 7361 | 80.75 | 91.1579 | 4,4 | TD | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Size | Wt/Grade | Bottom | Top | Date Set | Mud Wt. | 8.9 | 0 | 0 | 0 | 0
Conductor |  | 20 | 52.78 / B | 50 | 0' | 0 | Vis | 40 | 0 | 0 | 0 | 0
Surface Casing |  | 13.375 | 54.50 / J-55 | 1177 | 0' | 2018-05-24 | pH | 10 | 0 | 0 | 0 | 0
Intermediate Csg |  | 0 | 0 | 0 | 0 | 0 | API WL | 0
Intermediate 2 Csg |  | 0 | 0 | 0 | 0 | 0 | Chlorides | 40000
Production Casing |  | 0 | 0 | 0 | 0 | 0 | OWR | 0
Surface Rig Spud Date |  | 2018-05-22 | Time | 19:30 | Rig Pause Date |  | 0 | Time | 0:00
Surface Rig Release Date |  | 2018-05-24 | Time | 13:30 | Rig Resume Date |  | 0 | Time | 0:00
Rig Spud Date |  | 2018-06-23 | Time | 9:15 | Rig Release Date |  | 0 | Time | 0:00

## Report (10)
Well Name | Gwendolyn #2612 LB |  |  | Date | 2018-06-30 |  | Report # | 10 | Depth | 8538 | Footage |  | Planned TD | 8518 | Pad Location | 2-2
Op at RT | Circulating @ 5310' |  |  |  |  | Daily Cost | 141598 |  | Deviation Surveys
Contr/Rig # | Precision Rig 593 |  |  | Total Days | 8.6146 | Total Cost | 1073097 |  | MD | Angle | Azimuth | TVD | DLS | +N/-S | +E/-W | Closure D | Closure A | Hole Section Codes
Mud WT. | Vis | PV | YP | Gels | API WL | pH | Solids | Chlorides | 8479' | 2.3 | 62.92 | 8472.79 | 0.22 | 129.4 | -20.2 | 130.97 | 351.13 | 1 | Surface
8.3 | 27 | [16 empty] | 2 | Intermediate
HTHP | OWR | ES | WPS | LGS | 6 RPM | 3 RPM | Diesel Rate | Water Rate | [9 empty] | 3 | Intermediate 2
[18 empty] | 4 | Production
Diesel Daily | Diesel Total | +Gain/-Loss | Cntrfg Hrs | Torque and Drag Summary | [8 empty] | 0
|  |  |  | Depth | Torque | Rot. wt. | PU wt. | SO wt. | [9 empty] | IADC OP Codes
Mud Product Used Last 24 hours |  |  |  | 8270' | 12 to 14 | 255 | 260 | 240 | [9 empty] | 1 | Rig Up and Tear Down
[18 empty] | 2 | Drill Actual
[18 empty] | 3 | Reaming
[18 empty] | 4 | Coring
Drill Pipe Chemical Used Last 24 hours | [17 empty] | 5 | Condition Mud and Circulate
[18 empty] | 6 | Trips
[9 empty] | Last Survey Proximity to Plan Line |  |  |  | A/B | 13 B | L/R | 23 R |  | 7 | Lubricate Rig
From | To | Hours | Op Code | Activity for Previous 24 Hours | [13 empty] | 8 | Repair Rig
6:00 | 10:00 | 4 | 2.12 | Cont to cement 2nd stage per prog | [13 empty] | 9 | Cut Off Drilling Line
10:00 | 10:30 | 0.5 | 2.12 | Flush BOP, Flowline and rig down cementers | [13 empty] | 10 | Deviation Survey
10:30 | 11:45 | 1.25 | 2.12 | Back off landing joint & Lay down, Rig down ext.bails & Casing elevators, Set packoff, Pull 40K, Test packoff 5000 psi. | [13 empty] | 11 | Wireline Logs
11:45 | 12:45 | 1 | 2.12 | Install wear bushing with cactus service man | [13 empty] | 12 | Run Casing and Cement
12:45 | 13:15 | 0.5 | 2.6 | Pick up and make up 8 3/4" bit, run 2 stands od 6 1/2" DC's | [13 empty] | 13 | Wait on Cement
13:15 | 14:15 | 1 | 2.6 | P/U HWDP from catwalk | [13 empty] | 14 | Nipple Up BOP
14:15 | 16:15 | 2 | 2.6 | Trip in hole f/ 837' t/ 5185' Tag cement @ 5185' | [13 empty] | 15 | Test BOP
16:15 | 16:45 | 0.5 | 2.6 | Install rotating head & Shaker screens, Fill pipe | [13 empty] | 16 | Drill Stem Test
16:45 | 18:00 | 1.25 | 2.2 | Drill out DV tool @ 5196' | [13 empty] | 17 | Plug Back
18:00 | 5:30 | 11.5 | 2.2 | Drill out DV tool @ 5196' WOB 4-26, RPM 30-70, GPM 500-600, | [13 empty] | 18 | Squeeze Cement
5:30 | 6:00 | 0.5 | 2.5 | Circulate bottoms up. | [13 empty] | 19 | Fishing
6:00 | [17 empty] | 20 | Directional Work
0:00 | [17 empty] | 21 | Non Productive Time
0:00 | [17 empty] | 22
0:00 | [17 empty] | 23
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
TOTAL HOURS |  | 24 |  | Drilling Hrs: Fresh water gel tanks 500 Shaker Screens 0 RRC # 132473
Bit # | Size | Mfg | Type | Part | SN | Jets | In | Out | Ftg | Hrs | ROP | Grade | Gauge | Rsn Pulled | Comments
1 | 17.5 | PDC Logic | KS1963AR |  | 17111528 | 8X16 | 40 | 1177 | 1137 | 20.5 | 55.4634 | 1,1 | In | TD | Surface
2 | 12.25 | Ulterra | CF616M | U03001 | 39972 | 6 X 16 | 1177 | 8538 | 7361 | 80.75 | 91.1579 | 4,4 | In | TD | Intermediate
3 | 8.75 | Ulterra | CF 516 | U02789 | 34022 | 5 X 14 | 8538 | [7 empty] | Drill Out
BHA # | Description | [7 empty] | BHA Lngth | Motor Mfg | Size | Bend | Stab OD | Fixed/Adj | Lobes/Stages | RPG | SN
1 | Bit, Bit Sub, Shock Sub, True Fire, 8" DC, IBS, 8" DC, X/O, 5-6" DC's | [7 empty] | 237.43
2 | 12 1/4" bit, Motor #1, 11 3/4" Stab, UBHO, 2-NMDC, 11 3/4" Stab, 6-8" DC's, X/O, 12-6 1/2" DC's, X/O | [7 empty] | 660.53 | Renegade | 9 5/8 | 1.5 | 11.5 | Fixed | 7/8: 4.0 | .166 | RDM 911
3 | 8 3/4" bit, Bit sub, 6-6 1/2" DC's, X/O, 7 Stands HWDP, | [7 empty] | 837.8
|  | size | Wt. | Grade | Conn. | Jts | Length | Jts / Loc | String Volume |  |  |  | Size | Wt/Grade | Bottom | Top | Date Set
Drill Pipe (bottom) |  | 5 | 19.5 | S-135 | 4.5 IF |  |  |  | 81.2 | bbls. | Conductor |  | 20 | 52.78 / B | 50 | 0'
Drill Pipe (middle) |  | 5 | 49.8 | HWDP | 4.5 IF | 27 | 653.43 | 27 |  |  | Surface Casing |  | 13.375 | 54.50 / J-55 | 1177 | 0' | 2018-05-24
Drill Pipe (top) |  | 5 | 19.5 | S-135 | 4.5 IF | 50 | 4472.82 | 443 |  |  | Intermediate Csg |  | 9.625 | 40# /HCL80 | 8515 | 0' | 2018-06-29
Assumed Pump Eff. |  | Pump No. 1 |  | 95% | Pump No. 2 |  | 95% | Slow Pump Rate/Press |  |  | Intermediate 2 Csg
| Type | Liner OD | Length | GPS (100%) | SPM | GPM | Press | Depth | SPM | Pressure | Production Casing
Pump No. 1 | FB-1600 | 6 | 12 | 4.4 | 72 | 300.96 | 1097 | 8091 | 30 | 240 | Personnel Summary |  |  | Contact Information
Pump No. 2 | FB-1600 | 6 | 12 | 4.4 | 72 | 300.96 | 1097 | 8091 | 30 | 250 | Rig Crew Days |  | 6 | Foreman Days |  | Richard Hardwick
Surface Rig Spud Date |  | 2018-05-22 | Time | 19:30 | Loads/bbls FW Hauled |  |  | Item | Serial Number |  | Rig Crew Nights |  | 6 | Phone |  | (432)553-6153
Surface Rig Release Date |  | 2018-05-24 | Time | 13:30 | Loads/bbls BW Hauled |  |  | Stab 1 |  |  | Toolpusher |  | 1 | Foreman Nights |  | Randall Blue
Rig Spud Date |  | 2018-06-23 | Time | 9:15 | Loads/bbls Res Hauled |  | 5990 bbls | Stab 2 |  |  | Company Formen |  | 2 | Phone |  | (325)315-3200
Rig Pause Date |  |  | Time |  | Loads Gel Hauled |  |  | Stab 3 |  |  | Directional Drillers |  | 2 | Toolpusher |  | Doug Stovall
Rig Resume Date |  |  | Time |  | Loads Barite Hauled |  | 2 | Surv Tool |  |  | MWD |  | 2 | Phone |  | (940) 297-7726
Rig Release Date |  |  | Time |  | Loads OBM Cuttings |  |  | Bit Sub |  |  | Mud Engineer |  |  | Directional Days |  | Wesley Teeter
Incident/Safety Information | [7 empty] | Shock Sub |  |  | Solids Control |  |  | Phone |  | (817) 408-6235
No accidents reported last 24 hours | [7 empty] | Agitator |  |  | Other |  |  | Directional Nights |  | Shane Longmire
[8 empty] | NMDC |  |  | Total Personnel |  | 19 | Phone |  | (361) 354-4160
Well Name | Gwendolyn #2612 LB |  |  | Date | 2018-06-30 |  | Report # | 10 | Depth | 8538 | Footage | 0
Op at RT | Circulating @ 5310' |  |  |  |  | Daily Cost | 141598 |  | Deviation Surveys
Contr/Rig # | Precision Rig 593 |  |  | Total Days | 8.6146 | Total Cost | 1073097 |  | MD | Angle | Azimuth | TVD
Bit No. | Size | In | Out | Ftg | Hrs | ROP | Grade | Rsn Pulled | 8479' | 2.3 | 62.92 | 8472.79
1 | 17.5 | 40 | 1177 | 1137 | 20.5 | 55.4634 | 1,1 | TD | 0 | 0 | 0 | 0
2 | 12.25 | 1177 | 8538 | 7361 | 80.75 | 91.1579 | 4,4 | TD | 0 | 0 | 0 | 0
3 | 8.75 | 8538 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Size | Wt/Grade | Bottom | Top | Date Set | Mud Wt. | 8.3 | 0 | 0 | 0 | 0
Conductor |  | 20 | 52.78 / B | 50 | 0' | 0 | Vis | 27 | 0 | 0 | 0 | 0
Surface Casing |  | 13.375 | 54.50 / J-55 | 1177 | 0' | 2018-05-24 | pH | 0 | 0 | 0 | 0 | 0
Intermediate Csg |  | 9.625 | 40# /HCL80 | 8515 | 0' | 2018-06-29 | API WL | 0
Intermediate 2 Csg |  | 0 | 0 | 0 | 0 | 0 | Chlorides | 0
Production Casing |  | 0 | 0 | 0 | 0 | 0 | OWR | 0
Surface Rig Spud Date |  | 2018-05-22 | Time | 19:30 | Rig Pause Date |  | 0 | Time | 0:00
Surface Rig Release Date |  | 2018-05-24 | Time | 13:30 | Rig Resume Date |  | 0 | Time | 0:00
Rig Spud Date |  | 2018-06-23 | Time | 9:15 | Rig Release Date |  | 0 | Time | 0:00

## Report (11)
Well Name | Gwendolyn #2612 LB |  |  | Date | 2018-07-01 |  | Report # | 11 | Depth | 8615 | Footage | 77' | Planned TD | 8518 | Pad Location | 2-2
Op at RT | Drilling curve @ 8615' |  |  |  |  | Daily Cost | 97572 |  | Deviation Surveys
Contr/Rig # | Precision Rig 593 |  |  | Total Days | 9.6146 | Total Cost | 1170668 |  | MD | Angle | Azimuth | TVD | DLS | +N/-S | +E/-W | Closure D | Closure A | Hole Section Codes
Mud WT. | Vis | PV | YP | Gels | API WL | pH | Solids | Chlorides | 8479' | 2.3 | 62.92 | 8472.79 | 0.22 | 129.4 | -20.2 | 130.97 | 351.13 | 1 | Surface
8.1+ | 53 | 9 | 11 | 13 / 29 |  |  | 4.5 | 30000 | [9 empty] | 2 | Intermediate
HTHP | OWR | ES | WPS | LGS | 6 RPM | 3 RPM | Diesel Rate | Water Rate | [9 empty] | 3 | Intermediate 2
32 | 83 /17 | 623 | 229402 | 2.17 | 6 | 5 | 2.8 | 0.7 | [9 empty] | 4 | Production
Diesel Daily | Diesel Total | +Gain/-Loss | Cntrfg Hrs | Torque and Drag Summary | [8 empty] | 0
3141 | 3141 | -66 |  | Depth | Torque | Rot. wt. | PU wt. | SO wt. | [9 empty] | IADC OP Codes
Mud Product Used Last 24 hours |  |  |  | 8270' |  | 212 | 225 | 208 | [9 empty] | 1 | Rig Up and Tear Down
Lime 21, Benetone 910 2, Bentone 990 6, CaCl 15, | [17 empty] | 2 | Drill Actual
[18 empty] | 3 | Reaming
[18 empty] | 4 | Coring
Drill Pipe Chemical Used Last 24 hours | [17 empty] | 5 | Condition Mud and Circulate
[18 empty] | 6 | Trips
[9 empty] | Last Survey Proximity to Plan Line |  |  |  | A/B | 13 B | L/R | 23 R |  | 7 | Lubricate Rig
From | To | Hours | Op Code | Activity for Previous 24 Hours | [13 empty] | 8 | Repair Rig
6:00 | 6:15 | 0.25 | 2.5 | Cont. to circulate | [13 empty] | 9 | Cut Off Drilling Line
6:15 | 8:30 | 2.25 | 2.15 | Test casing to 1500 psi for 30 min, Lost 250 psi over 30 min, Checked all surface equipment and found no leaks. | [13 empty] | 10 | Deviation Survey
8:30 | 9:00 | 0.5 | 2.6 | Trip in hole f/ 5313 t/ 6670 | [13 empty] | 11 | Wireline Logs
9:00 | 9:30 | 0.5 | 2.5 | Circulate Full circulation | [13 empty] | 12 | Run Casing and Cement
9:30 | 11:00 | 1.5 | 2.15 | Check all valves, Test casing 1500 psi for 30 min. Good Test | [13 empty] | 13 | Wait on Cement
11:00 | 12:00 | 1 | 2.6 | Trip in hole f/ 6670' t/ 8452' | [13 empty] | 14 | Nipple Up BOP
12:00 | 12:30 | 0.5 | 2.2 | Drill shoe track f/ 8452' t/ 8532' | [13 empty] | 15 | Test BOP
12:30 | 13:30 | 1 | 2.5 | Circulate hole clean. | [13 empty] | 16 | Drill Stem Test
13:30 | 17:30 | 4 | 2.6 | T.O.O.H f/ 8532' t/ 322' | [13 empty] | 17 | Plug Back
17:30 | 18:00 | 0.5 | 2.7 | Rig service | [13 empty] | 18 | Squeeze Cement
18:00 | 18:45 | 0.75 | 2.6 | T.O.O.H f/ 322' w/ bha | [13 empty] | 19 | Fishing
18:45 | 20:15 | 1.5 | 2.20. | Pick up, make up, scribe and pulse test directional tools | [13 empty] | 20 | Directional Work
20:15 | 23:30 | 3.25 | 2.6 | T.I.H w/ drill pipe f/ 89 t/ 8000' | [13 empty] | 21 | Non Productive Time
23:30 | 24:00 | 0.5 | 2.6 | Pick up drill pipe off pipe cat f/ 8000' t/ 8538' | [13 empty] | 22
24:00 | 1:00 | 1 | 2.5 | Displace hole w/ OBM | [13 empty] | 23
1:00 | 2:00 | 1 | 2.2 | Rot f/ 8538' t/ 8573'/ 35'/ 35 FPH/ WOB 20/ RPM 20/ GPM 600/ MRPM 173/ TQ 5-7 (flow check- no flow)
2:00 | 2:45 | 0.75 | 2.2 | (Curve) Slide/ Rot f/ 8573' t/ 8595'/ 22'/ 29.3 FPH/ WOB 20/ RPM 0-25/ GPM 600/ MRPM 173
2:45 | 3:15 | 0.5 | 2.7 | Rig service
3:15 | 5:30 | 2.25 | 2.20. | Orientate MWD Tool for corrections
5:30 | 6:00 | 0.5 | 4.2 | (Curve) Slide/ Rot f/ 8595' t/ 8615'/ 20'/ 40 FPH/ WOB 20-30/ RPM 0/ GPM 600/ MRPM 173
6:00
0:00
0:00
0:00
0:00
0:00 |  |  |  | KOP 8573'
TOTAL HOURS |  | 24 |  | Drilling Hrs: 2.25 OBM on location 2102 Shaker Screens 8-230s RRC # 132473
Bit # | Size | Mfg | Type | Part | SN | Jets | In | Out | Ftg | Hrs | ROP | Grade | Gauge | Rsn Pulled | Comments
1 | 17.5 | PDC Logic | KS1963AR |  | 17111528 | 8X16 | 40 | 1177 | 1137 | 20.5 | 55.4634 | 1,1 | In | TD | Surface
2 | 12.25 | Ulterra | CF616M | U03001 | 39972 | 6 X 16 | 1177 | 8538 | 7361 | 80.75 | 91.1579 | 4,4 | In | TD | Intermediate
3 | 8.75 | Ulterra | CF 516 | U02789 | 34022 | 5 X 14 | 8538 | 8538 | 0 |  |  | 1,6 | In | TD | Drill Out
4 | 8.5 | Ulterra | CF 516 | U02888 | 41687 | 5 X 16 | 8538 | 8615 | 77 | 2.25 | 34.2222 |  |  |  | Curve
BHA # | Description | [7 empty] | BHA Lngth | Motor Mfg | Size | Bend | Stab OD | Fixed/Adj | Lobes/Stages | RPG | SN
1 | Bit, Bit Sub, Shock Sub, True Fire, 8" DC, IBS, 8" DC, X/O, 5-6" DC's | [7 empty] | 237.43
2 | 12 1/4" bit, Motor #1, 11 3/4" Stab, UBHO, 2-NMDC, 11 3/4" Stab, 6-8" DC's, X/O, 12-6 1/2" DC's, X/O | [7 empty] | 660.53 | Renegade | 9 5/8 | 1.5 | 11.5 | Fixed | 7/8: 4.0 | .166 | RDM 911
3 | 8 3/4" bit, Bit sub, 6-6 1/2" DC's, X/O, 7 Stands HWDP, | [7 empty] | 837.8
4 | Bit, Motor #1, UBHO, 2-NMDC's | [7 empty] | 89.5 | Renagade | 6.75 | 2.25 |  | Fixed | 7/8: 5.0 | .288 | RDM6839
|  | size | Wt. | Grade | Conn. | Jts | Length | Jts / Loc | String Volume |  |  |  | Size | Wt/Grade | Bottom | Top | Date Set
Drill Pipe (bottom) |  | 5 | 19.5 | S-135 | 4.5 IF |  |  |  | 146 | bbls. | Conductor |  | 20 | 52.78 / B | 50 | 0'
Drill Pipe (middle) |  | 5 | 49.8 | HWDP | 4.5 IF |  |  | 27 |  |  | Surface Casing |  | 13.375 | 54.50 / J-55 | 1177 | 0' | 2018-05-24
Drill Pipe (top) |  | 5 | 19.5 | S-135 | 4.5 IF | 192 | 8595.16 | 443 |  |  | Intermediate Csg |  | 9.625 | 40# /HCL80 | 8515 | 0' | 2018-06-29
Assumed Pump Eff. |  | Pump No. 1 |  | 95% | Pump No. 2 |  | 95% | Slow Pump Rate/Press |  |  | Intermediate 2 Csg
| Type | Liner OD | Length | GPS (100%) | SPM | GPM | Press | Depth | SPM | Pressure | Production Casing
Pump No. 1 | FB-1600 | 5.5 | 12 | 3.7 | 85 | 298.775 | 2200 | 8573 | 30 | 300 | Personnel Summary |  |  | Contact Information
Pump No. 2 | FB-1600 | 5.5 | 12 | 3.7 | 85 | 298.775 | 2200 | 8573 | 30 | 320 | Rig Crew Days |  | 6 | Foreman Days |  | Richard Hardwick
Surface Rig Spud Date |  | 2018-05-22 | Time | 19:30 | Loads/bbls FW Hauled |  |  | Item | Serial Number |  | Rig Crew Nights |  | 6 | Phone |  | (432)553-6153
Surface Rig Release Date |  | 2018-05-24 | Time | 13:30 | Loads/bbls BW Hauled |  |  | Stab 1 |  |  | Toolpusher |  | 1 | Foreman Nights |  | Randall Blue
Rig Spud Date |  | 2018-06-23 | Time | 9:15 | Loads/bbls Res Hauled |  | 3840 bbls | Stab 2 |  |  | Company Formen |  | 2 | Phone |  | (325)315-3200
Rig Pause Date |  |  | Time |  | Loads Gel Hauled |  |  | Stab 3 |  |  | Directional Drillers |  | 2 | Toolpusher |  | Doug Stovall
Rig Resume Date |  |  | Time |  | Loads Barite Hauled |  |  | Surv Tool |  |  | MWD |  | 2 | Phone |  | (940) 297-7726
Rig Release Date |  |  | Time |  | Loads OBM Cuttings |  |  | Bit Sub |  |  | Mud Engineer |  | 1 | Directional Days |  | Wesley Teeter
Incident/Safety Information | [7 empty] | Shock Sub |  |  | Solids Control |  | 2 | Phone |  | (817) 408-6235
No accidents reported last 24 hours | [7 empty] | Agitator |  |  | Other |  |  | Directional Nights |  | Shane Longmire
[8 empty] | NMDC | 700940 / 700580 |  | Total Personnel |  | 22 | Phone |  | (361) 354-4160
Well Name | Gwendolyn #2612 LB |  |  | Date | 2018-07-01 |  | Report # | 11 | Depth | 8615 | Footage | 77'
Op at RT | Drilling curve @ 8615' |  |  |  |  | Daily Cost | 97572 |  | Deviation Surveys
Contr/Rig # | Precision Rig 593 |  |  | Total Days | 9.6146 | Total Cost | 1170668 |  | MD | Angle | Azimuth | TVD
Bit No. | Size | In | Out | Ftg | Hrs | ROP | Grade | Rsn Pulled | 8479' | 2.3 | 62.92 | 8472.79
1 | 17.5 | 40 | 1177 | 1137 | 20.5 | 55.4634 | 1,1 | TD | 0 | 0 | 0 | 0
2 | 12.25 | 1177 | 8538 | 7361 | 80.75 | 91.1579 | 4,4 | TD | 0 | 0 | 0 | 0
3 | 8.75 | 8538 | 8538 | 0 | 0 |  | 1,6 | TD | 0 | 0 | 0 | 0
4 | 8.5 | 8538 | 8615 | 77 | 2.25 | 34.2222 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Size | Wt/Grade | Bottom | Top | Date Set | Mud Wt. | 8.1+ | 0 | 0 | 0 | 0
Conductor |  | 20 | 52.78 / B | 50 | 0' | 0 | Vis | 53 | 0 | 0 | 0 | 0
Surface Casing |  | 13.375 | 54.50 / J-55 | 1177 | 0' | 2018-05-24 | pH | 0 | 0 | 0 | 0 | 0
Intermediate Csg |  | 9.625 | 40# /HCL80 | 8515 | 0' | 2018-06-29 | API WL | 0
Intermediate 2 Csg |  | 0 | 0 | 0 | 0 | 0 | Chlorides | 30000
Production Casing |  | 0 | 0 | 0 | 0 | 0 | OWR | 83 /17
Surface Rig Spud Date |  | 2018-05-22 | Time | 19:30 | Rig Pause Date |  | 0 | Time | 0:00
Surface Rig Release Date |  | 2018-05-24 | Time | 13:30 | Rig Resume Date |  | 0 | Time | 0:00
Rig Spud Date |  | 2018-06-23 | Time | 9:15 | Rig Release Date |  | 0 | Time | 0:00

## Report (12)
Well Name | Gwendolyn #2612 LB |  |  | Date | 2018-07-02 |  | Report # | 12 | Depth | 9311 | Footage | 696 | Planned TD | 17441 | Pad Location | 2-2
Op at RT | Drilling curve @ 9311' |  |  |  |  | Daily Cost | 51167 |  | Deviation Surveys
Contr/Rig # | Precision Rig 593 |  |  | Total Days | 10.6146 | Total Cost | 1221835 |  | MD | Angle | Azimuth | TVD | DLS | +N/-S | +E/-W | Closure D | Closure A | Hole Section Codes
Mud WT. | Vis | PV | YP | Gels | API WL | pH | Solids | Chlorides | 8636' | 9.74 | 282.74 | 8629.13 | 7.39 | 133.78 | -30.38 | 137.19 | 347.21 | 1 | Surface
8.1+ | 49 | 10 | 10 | 11 / 24 |  |  | 4.5 | 31000 | 8726' | 19.73 | 293.19 | 8716.07 | 11.44 | 141.46 | -51.83 | 150.66 | 339.88 | 2 | Intermediate
HTHP | OWR | ES | WPS | LGS | 6 RPM | 3 RPM | Diesel Rate | Water Rate | 8815' | 32.75 | 291.22 | 8795.73 | 14.66 | 156.16 | -88.24 | 179.36 | 330.53 | 3 | Intermediate 2
32 | 84 / 16 | 653 | 247935 | 2.08 | 6 | 5 | 2.45 | 1.05 | 8905' | 42.13 | 284.09 | 8867.11 | 11.01 | 170.97 | -140.88 | 221.54 | 320.51 | 4 | Production
Diesel Daily | Diesel Total | +Gain/-Loss | Cntrfg Hrs | Torque and Drag Summary |  |  |  |  | 8994' | 49.04 | 278.43 | 8929.39 | 8.99 | 183.18 | -203.18 | 273.56 | 312.04
2840 | 5963 | 29 |  | Depth | Torque | Rot. wt. | PU wt. | SO wt. | 9084' | 59.65 | 281 | 8981.78 | 12.01 | 195.61 | -275.13 | 337.58 | 305.41 | IADC OP Codes
Mud Product Used Last 24 hours |  |  |  | 8863' | 8 to 9 | 218 | 230 | 200 | 9173' | 65.68 | 291.36 | 9022.72 | 12.35 | 217.77 | -350.82 | 412.92 | 301.83 | 1 | Rig Up and Tear Down
Lime 48, Benetone 910 6, Bentone 990 16, CaCl 45, Primary 1, Rhoe mod 1 |  |  |  | 9133' | 10 to 15 | 217 | 237 | 203 | 9263' | 67.82 | 302.59 | 9058.34 | 11.7 | 255.26 | -424.33 | 495.19 | 301.03 | 2 | Drill Actual
[18 empty] | 3 | Reaming
[18 empty] | 4 | Coring
Drill Pipe Chemical Used Last 24 hours | [17 empty] | 5 | Condition Mud and Circulate
[18 empty] | 6 | Trips
[9 empty] | Last Survey Proximity to Plan Line |  |  |  | A/B | 22 A | L/R | 11 R |  | 7 | Lubricate Rig
From | To | Hours | Op Code | Activity for Previous 24 Hours | [13 empty] | 8 | Repair Rig
6:00 | 7:00 | 1 | 4.2 | (Curve) Slide/ Rot f/ 8615' t/ 8684'/ 69' FPH/ WOB 20-30/ RPM 0/ GPM 600/ MRPM 173 | [13 empty] | 9 | Cut Off Drilling Line
7:00 | 8:00 | 1 | 4. 20 | Orientate for MWD corrections | [13 empty] | 10 | Deviation Survey
8:00 | 15:45 | 7.75 | 4.2 | (Curve) Slide f/ 8684' t/ 8863'/ 179'/ 23 FPH/ WOB 20-30/ RPM 0/ GPM 500-600/ MRPM 144-173 | [13 empty] | 11 | Wireline Logs
15:45 | 16:15 | 0.5 | 4.7 | Rig service | [13 empty] | 12 | Run Casing and Cement
16:15 | 18:00 | 1.75 | 4.2 | (Curve) Slide/Rot f/ 8863' t/ 8943'/ 60'/ 34.3 FPH/ WOB 20-30/ RPM 0-25/ GPM 500/ MRPM 144 | [13 empty] | 13 | Wait on Cement
18:00 | 3:00 | 9 | 4.2 | (Curve) Slide/ Rot f/ 8943' t/ 9221'/ 278'/ 30.9 FPH/ WOB 20-40/ RPM 0-25/ GPM 500/ MRPM 144 | [13 empty] | 14 | Nipple Up BOP
3:00 | 3:30 | 0.5 | 4.7 | Rig service | [13 empty] | 15 | Test BOP
3:30 | 6:00 | 2.5 | 4.2 | (Curve) Slide/ Rot f/ 9221' t/ 9311'/ 90'/ 36 FPH/ WOB 20-40/ RPM 0-25/ GPM 500/ MRPM 144 | [13 empty] | 16 | Drill Stem Test
6:00 | [17 empty] | 17 | Plug Back
0:00 | [17 empty] | 18 | Squeeze Cement
0:00 | [17 empty] | 19 | Fishing
0:00 | [17 empty] | 20 | Directional Work
0:00 | [17 empty] | 21 | Non Productive Time
0:00 | [17 empty] | 22
0:00 | [17 empty] | 23
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00 |  |  |  | KOP 8573'
TOTAL HOURS |  | 24 |  | Drilling Hrs: 22 OBM on location 2131 Shaker Screens 0 RRC # 132473
Bit # | Size | Mfg | Type | Part | SN | Jets | In | Out | Ftg | Hrs | ROP | Grade | Gauge | Rsn Pulled | Comments
1 | 17.5 | PDC Logic | KS1963AR |  | 17111528 | 8X16 | 40 | 1177 | 1137 | 20.5 | 55.4634 | 1,1 | In | TD | Surface
2 | 12.25 | Ulterra | CF616M | U03001 | 39972 | 6 X 16 | 1177 | 8538 | 7361 | 80.75 | 91.1579 | 4,4 | In | TD | Intermediate
3 | 8.75 | Ulterra | CF 516 | U02789 | 34022 | 5 X 14 | 8538 | 8538 | 0 |  |  | 1,6 | In | TD | Drill Out
4 | 8.5 | Ulterra | CF 516 | U02888 | 41687 | 5 X 16 | 8538 | 9311 | 773 | 24.25 | 31.8763 |  |  |  | Curve
BHA # | Description | [7 empty] | BHA Lngth | Motor Mfg | Size | Bend | Stab OD | Fixed/Adj | Lobes/Stages | RPG | SN
1 | Bit, Bit Sub, Shock Sub, True Fire, 8" DC, IBS, 8" DC, X/O, 5-6" DC's | [7 empty] | 237.43
2 | 12 1/4" bit, Motor #1, 11 3/4" Stab, UBHO, 2-NMDC, 11 3/4" Stab, 6-8" DC's, X/O, 12-6 1/2" DC's, X/O | [7 empty] | 660.53 | Renegade | 9 5/8 | 1.5 | 11.5 | Fixed | 7/8: 4.0 | .166 | RDM 911
3 | 8 3/4" bit, Bit sub, 6-6 1/2" DC's, X/O, 7 Stands HWDP, | [7 empty] | 837.8
4 | Bit, Motor #1, UBHO, 2-NMDC's | [7 empty] | 89.5 | Renegade | 6.75 | 2.25 |  | Fixed | 7/8: 5.0 | .288 | RDM6839
|  | size | Wt. | Grade | Conn. | Jts | Length | Jts / Loc | String Volume |  |  |  | Size | Wt/Grade | Bottom | Top | Date Set
Drill Pipe (bottom) |  | 5 | 19.5 | S-135 | 4.5 IF |  |  |  | 156.5 | bbls. | Conductor |  | 20 | 52.78 / B | 50 | 0'
Drill Pipe (middle) |  | 5 | 49.8 | HWDP | 4.5 IF |  |  | 27 |  |  | Surface Casing |  | 13.375 | 54.50 / J-55 | 1177 | 0' | 2018-05-24
Drill Pipe (top) |  | 5 | 19.5 | S-135 | 4.5 IF | 206 | 9221.68 | 443 |  |  | Intermediate Csg |  | 9.625 | 40# /HCL80 | 8515 | 0' | 2018-06-29
Assumed Pump Eff. |  | Pump No. 1 |  | 95% | Pump No. 2 |  | 95% | Slow Pump Rate/Press |  |  | Intermediate 2 Csg
| Type | Liner OD | Length | GPS (100%) | SPM | GPM | Press | Depth | SPM | Pressure | Production Casing
Pump No. 1 | FB-1600 | 5.5 | 12 | 3.7 | 72 | 253.08 | 2200 | 9221 | 30 | 430 | Personnel Summary |  |  | Contact Information
Pump No. 2 | FB-1600 | 5.5 | 12 | 3.7 | 72 | 253.08 | 2200 | 9221 | 30 | 440 | Rig Crew Days |  | 6 | Foreman Days |  | Richard Hardwick
Surface Rig Spud Date |  | 2018-05-22 | Time | 19:30 | Loads/bbls FW Hauled |  |  | Item | Serial Number |  | Rig Crew Nights |  | 6 | Phone |  | (432)553-6153
Surface Rig Release Date |  | 2018-05-24 | Time | 13:30 | Loads/bbls BW Hauled |  |  | Stab 1 |  |  | Toolpusher |  | 1 | Foreman Nights |  | Randall Blue
Rig Spud Date |  | 2018-06-23 | Time | 9:15 | Loads/bbls Res Hauled |  | 750 bbls | Stab 2 |  |  | Company Formen |  | 2 | Phone |  | (325)315-3200
Rig Pause Date |  |  | Time |  | Loads Gel Hauled |  |  | Stab 3 |  |  | Directional Drillers |  | 2 | Toolpusher |  | Doug Stovall
Rig Resume Date |  |  | Time |  | Loads Barite Hauled |  |  | Surv Tool |  |  | MWD |  | 2 | Phone |  | (940) 297-7726
Rig Release Date |  |  | Time |  | Loads OBM Cuttings |  |  | Bit Sub |  |  | Mud Engineer |  | 1 | Directional Days |  | Wesley Teeter
Incident/Safety Information | [7 empty] | Shock Sub |  |  | Solids Control |  | 2 | Phone |  | (817) 408-6235
No accidents reported last 24 hours | [7 empty] | Agitator |  |  | Other |  |  | Directional Nights |  | Shane Longmire
[8 empty] | NMDC | 700940 / 700580 |  | Total Personnel |  | 22 | Phone |  | (361) 354-4160
Well Name | Gwendolyn #2612 LB |  |  | Date | 2018-07-02 |  | Report # | 12 | Depth | 9311 | Footage | 696
Op at RT | Drilling curve @ 9311' |  |  |  |  | Daily Cost | 51167 |  | Deviation Surveys
Contr/Rig # | Precision Rig 593 |  |  | Total Days | 10.6146 | Total Cost | 1221835 |  | MD | Angle | Azimuth | TVD
Bit No. | Size | In | Out | Ftg | Hrs | ROP | Grade | Rsn Pulled | 8636' | 9.74 | 282.74 | 8629.13
1 | 17.5 | 40 | 1177 | 1137 | 20.5 | 55.4634 | 1,1 | TD | 8726' | 19.73 | 293.19 | 8716.07
2 | 12.25 | 1177 | 8538 | 7361 | 80.75 | 91.1579 | 4,4 | TD | 8815' | 32.75 | 291.22 | 8795.73
3 | 8.75 | 8538 | 8538 | 0 | 0 |  | 1,6 | TD | 8905' | 42.13 | 284.09 | 8867.11
4 | 8.5 | 8538 | 9311 | 773 | 24.25 | 31.8763 | 0 | 0 | 8994' | 49.04 | 278.43 | 8929.39
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 9084' | 59.65 | 281 | 8981.78
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 9173' | 65.68 | 291.36 | 9022.72
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 9263' | 67.82 | 302.59 | 9058.34
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Size | Wt/Grade | Bottom | Top | Date Set | Mud Wt. | 8.1+ | 0 | 0 | 0 | 0
Conductor |  | 20 | 52.78 / B | 50 | 0' | 0 | Vis | 49 | 0 | 0 | 0 | 0
Surface Casing |  | 13.375 | 54.50 / J-55 | 1177 | 0' | 2018-05-24 | pH | 0 | 0 | 0 | 0 | 0
Intermediate Csg |  | 9.625 | 40# /HCL80 | 8515 | 0' | 2018-06-29 | API WL | 0
Intermediate 2 Csg |  | 0 | 0 | 0 | 0 | 0 | Chlorides | 31000
Production Casing |  | 0 | 0 | 0 | 0 | 0 | OWR | 84 / 16
Surface Rig Spud Date |  | 2018-05-22 | Time | 19:30 | Rig Pause Date |  | 0 | Time | 0:00
Surface Rig Release Date |  | 2018-05-24 | Time | 13:30 | Rig Resume Date |  | 0 | Time | 0:00
Rig Spud Date |  | 2018-06-23 | Time | 9:15 | Rig Release Date |  | 0 | Time | 0:00

## Report (13)
Well Name | Gwendolyn #2612 LB |  |  | Date | 2018-07-03 |  | Report # | 13 | Depth | 9652 | Footage | 341 | Planned TD | 17441 | Pad Location | 2-2
Op at RT | Slip and cut drilling line |  |  |  |  | Daily Cost | 103436 |  | Deviation Surveys
Contr/Rig # | Precision Rig 593 |  |  | Total Days | 11.6146 | Total Cost | 1325271 |  | MD | Angle | Azimuth | TVD | DLS | +N/-S | +E/-W | Closure D | Closure A | Hole Section Codes
Mud WT. | Vis | PV | YP | Gels | API WL | pH | Solids | Chlorides | 9352' | 69.77 | 314.01 | 9090.62 | 12.16 | 306.62 | -489.27 | 577.41 | 302.07 | 1 | Surface
8.2+ | 52 | 10 | 10 | 12 / 23 |  |  | 5 | 30000 | 9442' | 73.84 | 324.07 | 9118.78 | 11.54 | 371.13 | 545.15 | 659.49 | 304.25 | 2 | Intermediate
HTHP | OWR | ES | WPS | LGS | 6 RPM | 3 RPM | Diesel Rate | Water Rate | 9604' | 83.09 | 338.06 | 9149.05 | 7.8 | 510.78 | -620.25 | 803.49 | 309.47 | 3 | Intermediate 2
32 | 84 / 16 | 609 | 241878 | 2.39 | 6 | 5 | 0 | [10 empty] | 4 | Production
Diesel Daily | Diesel Total | +Gain/-Loss | Cntrfg Hrs | Torque and Drag Summary
1622 | 7605 | 10 |  | Depth | Torque | Rot. wt. | PU wt. | SO wt. | [9 empty] | IADC OP Codes
Mud Product Used Last 24 hours |  |  |  | 9400' | 10, | 215 | 232 | 202 | [9 empty] | 1 | Rig Up and Tear Down
Lime 22, Benetone 910 2, Bentone 990 6, CaCl 10, Primary 0, Rhoe mod 0, Bar 7 tons | [17 empty] | 2 | Drill Actual
[18 empty] | 3 | Reaming
[18 empty] | 4 | Coring
Drill Pipe Chemical Used Last 24 hours | [17 empty] | 5 | Condition Mud and Circulate
[18 empty] | 6 | Trips
[9 empty] | Last Survey Proximity to Plan Line |  |  |  | A/B | OTL | L/R | 15 R |  | 7 | Lubricate Rig
From | To | Hours | Op Code | Activity for Previous 24 Hours | [13 empty] | 8 | Repair Rig
6:00 | 17:30 | 11.5 | 4.2 | (Curve) Slide/ Rot f/ 9311' t/ 9652'/ 341'/ 29.7 FPH/ WOB 20-40/ RPM 0-25/ GPM 500/ MRPM 144 | [13 empty] | 9 | Cut Off Drilling Line
17:30 | 18:30 | 1 | 4.3 | Working tight spot @ 9652' | [13 empty] | 10 | Deviation Survey
18:30 | 19:30 | 1 | 4.5 | Circulate bottoms up 6000 stks @ 600gpm. Flow check | [13 empty] | 11 | Wireline Logs
19:30 | 20:30 | 1 | 4.6 | T.O.O.H f/ 9652' t/ 8500' wet | [13 empty] | 12 | Run Casing and Cement
20:30 | 23:30 | 3 | 4.6 | T.O.O.H f/ 8500' t/ 89' | [13 empty] | 13 | Wait on Cement
23:30 | 24:15 | 0.75 | 4.20. | Lay down directional tools | [13 empty] | 14 | Nipple Up BOP
24:15 | 1:15 | 1 | 4.20. | Pick up, make up, scribe and pulse directional tools | [13 empty] | 15 | Test BOP
1:15 | 5:00 | 3.75 | 4.6 | T.I.H w/ drill pipe f/ 103' t/ 8493' | [13 empty] | 16 | Drill Stem Test
5:00 | 6:00 | 1 | 4.9 | Slip & cut 96' of drill line | [13 empty] | 17 | Plug Back
6:00 | [17 empty] | 18 | Squeeze Cement
0:00 | [17 empty] | 19 | Fishing
0:00 | [17 empty] | 20 | Directional Work
0:00 | [17 empty] | 21 | Non Productive Time
0:00 | [17 empty] | 22
0:00 | [17 empty] | 23
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00 |  |  |  | Agitator 22 stds above BHA. Before 650 psi After 780 psi @ 100 spm
0:00 |  |  |  | KOP 8573'
TOTAL HOURS |  | 24 |  | Drilling Hrs: 11.5 OBM on location 2141 Shaker Screens 0 RRC # 132473
Bit # | Size | Mfg | Type | Part | SN | Jets | In | Out | Ftg | Hrs | ROP | Grade | Gauge | Rsn Pulled | Comments
1 | 17.5 | PDC Logic | KS1963AR |  | 17111528 | 8X16 | 40 | 1177 | 1137 | 20.5 | 55.4634 | 1,1 | In | TD | Surface
2 | 12.25 | Ulterra | CF616M | U03001 | 39972 | 6 X 16 | 1177 | 8538 | 7361 | 80.75 | 91.1579 | 4,4 | In | TD | Intermediate
3 | 8.75 | Ulterra | CF 516 | U02789 | 34022 | 5 X 14 | 8538 | 8538 | 0 |  |  | 1,6 | In | TD | Drill Out
4 | 8.5 | Ulterra | CF 516 | U02888 | 41687 | 5 X 16 | 8538 | 9652 | 1114 | 35.75 | 31.1608 | 1,2 | In | BHA | Curve, 1 Chipped Cutter
5 | 8.5 | Ulterra | CF616 | UO2850 | 37830 | 6 X 16 | 9652 | [7 empty] | Lateral
BHA # | Description | [7 empty] | BHA Lngth | Motor Mfg | Size | Bend | Stab OD | Fixed/Adj | Lobes/Stages | RPG | SN
1 | Bit, Bit Sub, Shock Sub, True Fire, 8" DC, IBS, 8" DC, X/O, 5-6" DC's | [7 empty] | 237.43
2 | 12 1/4" bit, Motor #1, 11 3/4" Stab, UBHO, 2-NMDC, 11 3/4" Stab, 6-8" DC's, X/O, 12-6 1/2" DC's, X/O | [7 empty] | 660.53 | Renegade | 9 5/8 | 1.5 | 11.5 | Fixed | 7/8: 4.0 | .166 | RDM 911
3 | 8 3/4" bit, Bit sub, 6-6 1/2" DC's, X/O, 7 Stands HWDP, | [7 empty] | 837.8
4 | Bit, Motor #2, UBHO, 2-NMDC's | [7 empty] | 89.5 | Renegade | 6.75 | 2.25 |  | Fixed | 7/8: 5.0 | .288 | RDM6839
5 | Bit, Motor #3, 7 7/8 Stab, UBHO, 2-NMDC's | [7 empty] | 103.57 | Sniper | 6.81 | 1.75 |  | Fixed | 7/8: 5.0 | .288 | DR67086
|  | size | Wt. | Grade | Conn. | Jts | Length | Jts / Loc | String Volume |  |  |  | Size | Wt/Grade | Bottom | Top | Date Set
Drill Pipe (bottom) |  | 5 | 19.5 | S-135 | 4.5 IF | 188 | 8863.7 | 443 | 156.5 | bbls. | Conductor |  | 20 | 52.78 / B | 50 | 0'
Drill Pipe (middle) |  | 5 | 49.8 | HWDP | 4.5 IF |  |  | 21 |  |  | Surface Casing |  | 13.375 | 54.50 / J-55 | 1177 | 0' | 2018-05-24
Drill Pipe (top) |  | 5 | 19.5 | S-135 | 4.5 IF | [5 empty] | Intermediate Csg |  | 9.625 | 40# /HCL80 | 8515 | 0' | 2018-06-29
Assumed Pump Eff. |  | Pump No. 1 |  | 95% | Pump No. 2 |  | 95% | Slow Pump Rate/Press |  |  | Intermediate 2 Csg
| Type | Liner OD | Length | GPS (100%) | SPM | GPM | Press | Depth | SPM | Pressure | Production Casing
Pump No. 1 | FB-1600 | 5.5 | 12 | 3.7 | 72 | 253.08 | 2200 | 9221 | 30 | 430 | Personnel Summary |  |  | Contact Information
Pump No. 2 | FB-1600 | 5.5 | 12 | 3.7 | 72 | 253.08 | 2200 | 9221 | 30 | 440 | Rig Crew Days |  | 6 | Foreman Days |  | Richard Hardwick
Surface Rig Spud Date |  | 2018-05-22 | Time | 19:30 | Loads/bbls FW Hauled |  |  | Item | Serial Number |  | Rig Crew Nights |  | 6 | Phone |  | (432)553-6153
Surface Rig Release Date |  | 2018-05-24 | Time | 13:30 | Loads/bbls BW Hauled |  |  | Stab 1 | SD26528 |  | Toolpusher |  | 1 | Foreman Nights |  | Randall Blue
Rig Spud Date |  | 2018-06-23 | Time | 9:15 | Loads/bbls Res Hauled |  | 2940 bbls | Stab 2 |  |  | Company Formen |  | 2 | Phone |  | (325)315-3200
Rig Pause Date |  |  | Time |  | Loads Gel Hauled |  |  | Stab 3 |  |  | Directional Drillers |  | 2 | Toolpusher |  | Doug Stovall
Rig Resume Date |  |  | Time |  | Loads Barite Hauled |  |  | Surv Tool |  |  | MWD |  | 2 | Phone |  | (940) 297-7726
Rig Release Date |  |  | Time |  | Loads OBM Cuttings |  |  | Bit Sub |  |  | Mud Engineer |  | 1 | Directional Days |  | David Willis
Incident/Safety Information | [7 empty] | Shock Sub |  |  | Solids Control |  | 2 | Phone |  | (936) 671-1247
No accidents reported last 24 hours | [7 empty] | Agitator | 1243478-2 |  | Other |  |  | Directional Nights |  | Shane Longmire
[8 empty] | NMDC | 700940 / 700580 |  | Total Personnel |  | 22 | Phone |  | (361) 354-4160
Well Name | Gwendolyn #2612 LB |  |  | Date | 2018-07-03 |  | Report # | 13 | Depth | 9652 | Footage | 341
Op at RT | Slip and cut drilling line |  |  |  |  | Daily Cost | 103436 |  | Deviation Surveys
Contr/Rig # | Precision Rig 593 |  |  | Total Days | 11.6146 | Total Cost | 1325271 |  | MD | Angle | Azimuth | TVD
Bit No. | Size | In | Out | Ftg | Hrs | ROP | Grade | Rsn Pulled | 9352' | 69.77 | 314.01 | 9090.62
1 | 17.5 | 40 | 1177 | 1137 | 20.5 | 55.4634 | 1,1 | TD | 9442' | 73.84 | 324.07 | 9118.78
2 | 12.25 | 1177 | 8538 | 7361 | 80.75 | 91.1579 | 4,4 | TD | 9604' | 83.09 | 338.06 | 9149.05
3 | 8.75 | 8538 | 8538 | 0 | 0 |  | 1,6 | TD | 0 | 0 | 0 | 0
4 | 8.5 | 8538 | 9652 | 1114 | 35.75 | 31.1608 | 1,2 | BHA | 0 | 0 | 0 | 0
5 | 8.5 | 9652 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Size | Wt/Grade | Bottom | Top | Date Set | Mud Wt. | 8.2+ | 0 | 0 | 0 | 0
Conductor |  | 20 | 52.78 / B | 50 | 0' | 0 | Vis | 52 | 0 | 0 | 0 | 0
Surface Casing |  | 13.375 | 54.50 / J-55 | 1177 | 0' | 2018-05-24 | pH | 0 | 0 | 0 | 0 | 0
Intermediate Csg |  | 9.625 | 40# /HCL80 | 8515 | 0' | 2018-06-29 | API WL | 0
Intermediate 2 Csg |  | 0 | 0 | 0 | 0 | 0 | Chlorides | 30000
Production Casing |  | 0 | 0 | 0 | 0 | 0 | OWR | 84 / 16
Surface Rig Spud Date |  | 2018-05-22 | Time | 19:30 | Rig Pause Date |  | 0 | Time | 0:00
Surface Rig Release Date |  | 2018-05-24 | Time | 13:30 | Rig Resume Date |  | 0 | Time | 0:00
Rig Spud Date |  | 2018-06-23 | Time | 9:15 | Rig Release Date |  | 0 | Time | 0:00

## Rig Repairs Log
Rig Repair Log*
Well: | Gwendolyn #2612 LB
Contractor | Precision 593
Spud Date: | 5/22/18 @ 19:30 |  | Release Date :
Drlg Foremen: | Richard Hardwick / Randall Blue / Cody Keel / Jason Rhoudes
*This log is for downtime associated with rig repairs, including time
associated with holes in the DP/DC
Report Date | Rig Time (hrs) | Description/Comments
2018-06-24 | 0 | No Repairs
2018-06-25 | 0 | No Repairs
2018-06-26 | 0 | No Repairs
2018-06-27 | 0 | No Repairs
2018-06-28 | 0 | No Repairs
2018-06-29 | 0 | No Repairs
2018-06-30 | 0 | No Repairs
2018-07-01 | 0 | No Repairs
2018-07-02 | 0 | No Repairs
2018-07-03 | 0 | No Repairs
Total hours | 0